## Cover
BLM Q2 SDBIP 2023-24 REPORTING TEMPLATE
VISION
A participatory municipality that turns prevailing challenges into opportunities for growth and development through optimal utilization of available resources
MISSION
To ensure delivery of quality services through community participation and creation of an enabling environment for economic growth and job creation

## Q2 QTR SUMMARY PER DEPT (2)
Department | Total Second Quarter Targets | Targets Achieved | Targets not achieved | Achievement in Percentage
Corporate Services | 16 | 10 | 6 | 63%
Community Services | 28 | 18 | 10 | 64%
Economic Development & Planning | 8 | 4 | 4 | 50%
Budget & Treasury | 10 | 9 | 1 | 89%
Technical Services | 28 | 8 | 20 | 28%
Municipal Managers 'Office | 6 | 3 | 3 | 50%
Overall Total Targets | 96 | 52 | 44 | 54%
APPROVED BY
RAMOTHWALA RJ
MUNICIPAL MANAGER

## SDBIP per KPA (2)
APPROVED Q2 BLM SDBIP 2023-24 REPORT
BASIC SERVICES AND INFRASTRUCTURE DEVELOPMENT
NDP | BUILDING KEY CAPABILITIES(HUMAN,PHYSICAL AND INSTITUTIONAL
OUTCOME 9 | IMPROVE ACCESS TO BASIC SERVICES ( OUTPUT 2)
Project Details
Quarterly Projections
Project/KPI Number | Project Name | Project Description (major activities) | Strategic Objective | Location | Key Performance Indicator | 2022-23 Baseline | 2023-24 Annual Target | Q1 | Q2 | Q2 Actual Performance | Reason for variance | Corrective Measure | Q3 | Q4 | 2023-24 Budget | Portfolio of evidence | Responsible Department
BSID 1 | Electrical Equipment | Purchasing of identified Electrical equipment | To ensure minimal energy consuption by users as per the national energy reduction strategy | BLM | Number identified electrical equipment purchased by June 2024 | 25 Electrical equipment purchased by June 2023 | 30 Identified Electrical equipment purchased by June 2024 | Procurement processes | 10 Identified Electrical equipment purchased . | Target Achieved. 10 Identified Electrical equipments procured. | N\A | N\A | 10 Identified Electrical equipment purchased . | 10 Identified Electrical equipment purchased . | 1908000 | Proof of Purchase | Technical services
BSID 3 | Transformers | Purchasing and Installation of emergency Transformers | To ensure uninterrupted energy supply | BLM | Percentage ermegency transformers purchased and installed as an when required by June 2024 | 100% ermegency transformers purchased and installed as an when required. | 100 % Purchasing and Installation of emergency Transformers as an when required by June 2024 | 100 % Purchasing and Installation of emergency Transformers as an when required | 100 % Purchasing and Installation of emergency Transformers as an when required | Target Achieved. 100 % Purchasing and Installation of emergency Transformers as an when required | N\A | N\A | 100 % Purchasing and Installation of emergency Transformers as an when required | 100 % Purchasing and Installation of emergency Transformers as an when required | 207000 | Proof of Purchase and Transformer register | Technical services
BSID 4 | Transformers | Reconditioning of Transformers | To ensure uninterrupted energy supply | BLM | Number Transformers reconditioned by June 2024 | 16 Transformers reconditioned by June 2023 | 10 Transformers reconditioned by June 2024 | procurent processes | 5 Transformers reconditioned. | Target not Achieved.5 Transformers not reconditioned. | Delay in appointment of the service provider | Scm to fast-track the appointment of the service provider | N/A | 5 Transformers reconditioned. | R600 000.00 | Proof of Purchase and pictures | Technical services
BSID 7 | TID ROLL OVER | Replacement of meters installed before 2015 to STS6 compliant by November 2024 | To ensure uninterrupted energy supply | BLM | 4 Reports compiled on upgrading of meters by June 2024 |  | 4 Reports compiled on upgrading of meters by June 2024 | 1 Reports compiled on upgrading of meters | 1 Reports compiled on upgrading of meters | Target achieved. Report compiled. | N/A | N/A | 1 Reports compiled on upgrading of meters | 1 Reports compiled on upgrading of meters | R 2 500 000 | Reports | Budget & Treasury
BSID 8 | Poles | Purchasing and replacement of poles |  | BLM | Number Poles purchased and installed by June 2024 | 30 Poles purchased and installed at Grootpan, The-Grange and Simpson by June 2023 | 20 Poles purchased and at Mosehleng and Milbank by end of June 2024 | procurent processes | 10 Poles purchased and installed | Target not Achieved. 10 Poles not purchased and installed | Delay in appointment of the service provider | Scm to fast-track the appointment of the service provider | 10 Poles purchased and installed | N/A | R 200 000.00 | Proof of Purchase and pictures | Technical services
BSID 13 | Electrification of extensions | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Alldays village | Number households electrified and energized at Alldays Township by June 2024 | New indicator | 60 households electrified and energised at Alldays town by June 2024 | PLANNING STAGE - Inception, Concept and Viability, Design Development, | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor. | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the thrid quarter as construction companies alredy closed for builder holidays. | Construction stage – Surveying, Pegging, Digging of holes, Planting of poles, Stringing of MV and LV conductors. | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 60 connections at Alldays | 1,110,000,00 | Advert, appointment letters, site hand over minutes, pictures and Completion certificate | Technical services
BSID 14 | Electrification of extensions | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Mochemi village | Number households electrified and energized at Mochemi village by June 2024 | New Indicator | 25 households electrified and energised at Mochemi village by June 2024 | PLANNING STAGE - Inception, Concept and Viability, Design Development, | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor. | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Construction stage – Surveying, Pegging, Digging of holes, Planting of poles, Stringing of MV and LV conductors. | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 25 connections at Mochemi | R 350 000 | Advert, appointment letters, site hand over minutes, pictures and Completion certificate | Technical services
BSID 15(1) | Electrification of extensions | onfirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Bayswater village | Number households electrified and energized at Bayswater village by June 2024 | New indicator | 30 households electrified and energised at Bayswater village by June 2024 | PLANNING STAGE - Inception, Concept and Viability, Design Development, | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor done | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Construction stage – Surveying, Pegging, Digging of holes, Planting of poles, Stringing of MV and LV conductors. | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 30 connections at Bayswater | 240000 | Advert, appointment letters, site hand over minutes, pictures and Completion certificate | Technical services
BSID 15(2) | Electrification of extensions | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Mongalo village | Number households electrified and energized at Mongalo village by June 2024 | New indicator | 50 households electrified and energised at Mongalo village by June 2024 | PLANNING STAGE - Inception, Concept and Viability, Design Development, | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor done | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Construction stage – Surveying, Pegging, Digging of holes, Planting of poles, Stringing of MV and LV conductors. | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 50 connections at Mongalo | 1000000 | Advert, appointment letters, site hand over minutes, pictures and Completion certificate | Technical services
BSID 15(3) | Electrification of extensions | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Simpson village | Number households electrified and energized at Simpson village by June 2024 | New indicator | 25 households electrified and energised at Simpson village by June 2024 | PLANNING STAGE - Inception, Concept and Viability, Design Development, | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor done | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Construction stage – Surveying, Pegging, Digging of holes, Planting of poles, Stringing of MV and LV conductors. | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 25 connections at Simpson | 200000 | Advert, appointment letters, site hand over minutes, pictures and Completion certificate | Technical services
BSID 15(4) | Electrification of extensions | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Swartz village | Number households electrified and energized at Swartz village by June 2024 | New indicator | 45 households electrified and energised at Swartz village by June 2024 | PLANNING STAGE - Inception, Concept and Viability, Design Development, | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor done | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Construction stage – Surveying, Pegging, Digging of holes, Planting of poles, Stringing of MV and LV conductors. | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 45 connections at Swartz | 900000 | Advert, appointment letters, site hand over minutes, Quarterly Progress reports, pictures and Completion certificate | Technical services
BSID 15(5) | Electrification of extensions | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Sweethome village | Number households electrified and energized at Sweethome village by June 2024 | New indicator | 70 households electrified and energised at Sweethome village by June 2024 | PLANNING STAGE - Inception, Concept and Viability, Design Development, | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor done | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Construction stage – Surveying, Pegging, Digging of holes, Planting of poles, Stringing of MV and LV conductors. | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 70 connections at Sweethome | 1400000 | Advert, appointment letters, site hand over minutes, Quarterly Progress reports, pictures and Completion certificate | Technical services
BSID 16 | Construction of Senwabarwana Substation Phase 3 | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To provide sustainable energy to all households | Senwabarwana electricity substation Phase 3 | Substation constructed at Senwabarwana by June 2024 | Perimeter fence(120m), Drilling and equipping of borehole(01) and Building of Substation House(160m2) ,Paving (350m2),Access road (1.3km). Construction of Primary Plant Platform, Construction of Primary Plant Equipment Foundations, Supply and Installation of Primary Plant Equipments. | Procurement of 1 x 20MVA 132/22KV Power Transformer, 1 x NERC, 22KV Switchgear and Internal Access Road. | PLANNING STAGE - Inception, Concept and Viability, Design Development, Construction Tender Stage | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment, Construction Commencement | Target not Achieved.Construction stage – Appointment of Contractor done | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Construction stage (Procurement of 1 x 20MVA 132/22KV Power Transformer, 1 X NECR, 22KV Switchgear) | Construction of Access Road and Installation of Power Transformer, NECR and 22KV Switchgear | 27800000 | Advert, appointment letters, site hand over minutes, Quarterly Progress reports, pictures and Completion Certificate. | Technical services
BSID 17 | Roads (Maintenance) | Maintenance of roads | To maintain internal streets and access roads on continuous basis | Senwabarwana | Square meters of patching potholes, number of road signs and, square meters of road markings at Senwabarwana Internal Streets and Storm water done by June 2024 | 700 Square meters of patching potholes and 50 square meters of road markings at Senwabarwana Internal Streets by June 2023 | 800 Square meters of patching potholes, installation of 03 road signs and 50 square meters of road markings at Senwabarwana Internal Streets by June 2024 | Assessment and measurements on the status of the roads. | Procurement processes for appointment of service providers | Target Achieved. Procurement processes for appointment of service providers | N/A | N/A | Patching of 800sqm of potholes, installation of 03 road signs and 50sqm of road markings | N/A | 424000 | Photographs, Ward Councillors confirmation letter | Photographs, Ward Councillors confirmation letter
BSID 18 | Roads maintenance | Maintenance of roads | To maintain internal streets and access roads on continuous basis | Dilaeneng | Square meters patching of potholes, number of speed humps constructed, number of insatallation of road signs and kilometeres of sweeping and square meters road markings at Dilaeneng done by June 2024 | 100 Square meters of patching potholes and 10 square meters of road markings and 1km of sweeping at Dilaeneng Internal Streets by June 2023 | 50 Square meters of patching potholes, construction of 1 speed hump, installation of 02 road signs, 30 square meters of road markings and 1km of sweeping at Dilaeneng Internal Streets by June 2024 | Assessment and measurements on the status of the roads. Procurement processes for appointment of service providers | Patching of 50 sqm of potholes, construction of 1 speed hump, installation of 2 road signs, 1km of sweeping and 30 sqm of road markings | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | N/A | N/A | R 100 000.00 | Photographs, Ward Councillors confirmation letter | Technical services
BSID 19 | Roads (Miantenance) | Maintenance of roads | To maintain internal streets and access roads on continuous basis | Witten | Square meters of patching and square meters of road markings at Witten Internal Streets and Storm water done by June 2024 | 10 Square meters of patching concrete drift,5sqm of patching of potholes, 05 number of road signs and 50 sqm of road markings at Witten Internal Streets by June 2023 | 50 sqm of patching of potholes and 50 sqm of road markings at Witten Internal Streets by June 2024 | Assessment and measurements on the status of the roads. Procurement processes for appointment of service providers | Patching of 50 sqm potholes and 50 sqm of road markings | Target Not Achieved. Specification submitted for appointment of service provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | N/A | N/A | R 30 000.00 | Photographs, Ward Councillors confirmation letter | Technical services
BSID 20 | Roads (Maintenance) | Maintenance of roads |  | Puraspan | Number of road signs, sqm of road markings and construction of speed humps complete with markings at Puraspan Internal Streets by June 2024 | Installation of 20 road signs and construction of 05 speed humps complete with markings at Puraspan Internal Streets and Storm water done by June 2023. | Supply and installation of 20 road signs, 50sqm of road markings and construction of 05 speed humps complete with markings at Puraspan Internal Streets by June 2024 | Assessment and measurements on the status of the roads. Procurement processes for appointment of service providers | Installation of 20 road signs, 50sqm of road markings and construction of 05 speed humps complete with markings. | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | N/A | N/A | R 100 000.00 | Photographs, Ward Councillors confirmation letter | Technical services
BSID 21 | Roads (Maintenance) | Maintenance of roads |  | Avon | Number of road signs, square meters of road markings and km of sweeping at Avon Internal Streets and Storm water done by June 2024 | 50sq of road markings, installation of 05 road signs,3.0 km of sweeping and 50 square meters of patching potholes at Avon Internal Streets and Storm water done by June 2023 | 100sq of road markings, installation of 05 road signs and 3.0 km of sweeping at Avon Internal Streets and Storm water done by June 2024 | Assesment and measurements on the status of the roads. Procurement processes for appointment of service providers | 100sqm of road markings, installation of 05 road signs and 3.0 km of sweeping | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | N/A | N/A | R 50 000.00 | Photographs, Ward Councillors confirmation letter | Technical services
BSID 22 | Roads (Maintenance) | Maintenance of roads | To maintain internal streets and access roads on continuous basis | Indermark | Square meters of patching potholes, number of road signs, square meters and sqm of road markings at Indermark Internal Streets and Storm water done by June 2024 | 4 road signs installed , 100 square meters potholes patched and 1 kilometer sweeped at Indermark Internal Streets and Storm water done by June 2023 | Supply and installation of 4 road signs , 50sqm potholes patching and 50sqm of road markings and 1km sweeping at Indermark Internal Streets and Storm water done by June 2024 | Assesment and measurements on the status of the roads. | Procurement processes for appointment of service providers | Target Achieved. Procurement processes for appointment of service providers | N/A | N/A | Installation of 04 road signs, patching of 50sqm of potholes, 50sqm of road markings and 1km of sweeping | N/A | 50000 | Photographs, Ward Councillors confirmation letter | Technical services
BSID 23 | Roads (Maintenance) | Maintenance of roads |  | Kromhoek | Square meters of patching potholes, square meters and km of road markings at Kromhoek Internal Streets and Storm water done by June 2024 | 05 road signs installed, 50 square meters potholes patched, 50sqm of road markings and 1 kilometers sweeped at Kromhoek Internal Streets and Storm water done by June 2023 | 50 sqm of potholes patching, 50sqm of road markings and 2 kilometers sweeped at Kromhoek Internal Streets and Storm water done by June 2024. | Assesment and measurements on the status of the roads. | Procurement processes for appointment of service providers | Target Achieved. Procurement processes for appointment of service providers | N/A | N/A | Installation of 50 sqm of potholes patching, 50sqm of road markings and 2 kilometers sweeping | N/A | R50 00.00 | Photographs, Ward Councillors confirmation letter | Technical services
BSID 24 | Roads (Maintenance) | Maintenance of roads |  | Devrede | square meters of road markings and square meters of potholes patching at Devrede Internal Streets and Storm water done by June 2024 | 04 road signs installed and 2 speed hump constructed, 10sqm of concrete drift repairs and 1 kilometer sweeped at Devrede Internal Streets and Storm water done by June 2023 | 50sqm of potholes patching, 50 sqm of road markings and sweeping of 1 kilometer of internal street by June 2024 | Assesment and measurements on the status of the roads. Procurement processes for appointment of service providers | 50 sqm of potholes patching, 50 sqm of road markings and sweeping of 1 kilometer of internal street | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | N/A | N/A | R 50 000.00 | Photographs, Ward Councillors confirmation letter | Technical services
BSID 25 | Roads (Maintenance) | Maintenance of roads |  | Taaibosch | Number of road signs and construction of speed humps, km of sweeping and square meters of patching potholes, square meters and km of road markings at Taaibosch Internal Streets and Storm water done by June 2024 | Installation of 04 road signs, 150sqm of potholes patching, 50sqm of road markings and construction of 02 speed humps at Taaibosch Internal Streets and Storm water done by June 2023. | Installation of 05 road signs, 150 sqm of potholes patching, construction of 02 speed humps,50sqm of road markings at Taaibosch Internal Streets and Storm water done by June 2024. | Assesment and measurements on the status of the roads. Procurement processes for appointment of service providers | Installation of 04 road signs, 150 sqm of potholes patching, construction of 02 speed humps,50sqm of road markings | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | N/A | N/A | R 200 000.00 | Photographs, Ward Councillors confirmation letter | Technical services
BSID 26 | Roads (Maintenance) | Maintenance of roads |  | Alldays | Number of road signs and construction of speed humps, and square meters of patching potholes, square meters and km of road markings at Alldays Internal Streets and Storm water done by June 2024 | 15 road signs installed and 6 speed humps constructed, 200 square meters potholes patched and 50 sqm of road markings at Alldays Internal Streets and Storm water done by June 2023. | Installation of 12 road signs and construction of 06 speed humps, and 200 square meters of patching potholes, 50 square meters of road markings at Alldays Internal Streets and Storm water done by June 2024 | Assesment and measurements on the status of the roads. Procurement processes for appointment of service providers | Installation of 12 road signs and construction of 06 speed humps, and 50 square meters of road markings | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | 200 square meters of patching potholes | N/A | R 300 000.00 | Photographs, Ward Councillors confirmation letter | Technical services
BSID 27 | Roads (Maintenance) | Maintenance of roads |  | Desmond park | km of sweeping and square meters of road markings at Desmond Park Internal Streets and Storm water done by June 2024 | 25 road signs installed and 7 speed humps constructed, 50 square meters potholes patched and 1km of sweeping at Desmond park Internal Streets and Storm water done by June 2023. | 100sqm of road markings and 1km of sweeping at Desmond park Internal Streets and Storm water done by June 2024. | Assesment and measurements on the status of the roads. Procurement processes for appointment of service providers | 100sqm of road markings and 1km of sweeping | Target Not Achieved. Specification submitted for appointment of service provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | N/A | N/A | R 30 000.00 | Photographs, Ward Councillors confirmation letter | Technical services
BSID 28 | Roads (Maintenance) | Maintenance of roads |  | Millenium Park | Square meters and km of road markings and at Millennium Park Internal Streets and Storm water done by June 2024 | Installation of 10 road signs and 50 square meters of road markings at Millenium Park Internal Streets and Storm water done by June 2023 | 50 square meters of road markings and 1,1km of road markings at Millenium Park Internal Streets and Storm water done by June 2024 | Assesment and measurements on the status of the roads. Procurement processes for appointment of service providers | 50 square meters and 1,1km of road markings | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | N/A | N/A | R 50 000.00 | Photographs, Ward Councillors confirmation letter | Technical services
BSID 29 | Culverts | Construction of new culverts | To construct low water bridges | BLM | Number of culverts constructed complete with wing-walls and number of culverts purchased by June 2024 | 64 new culverts and 14 wingwalls constructed by June 2023 | 58 new culverts and 30 wingwalls constructed and 40 new culverts purchased by June 2024 | Assesment and measurements of the streams. Procurement of 40 new culverts. Construcion of 12 culverts and construction of 04 wingwalls | Construction of 22 culverts and construction of 08 wingwalls | Target Not Achieved. 06 x 900mm pipe culverts installed at Avon | Installation of 22 culverts not achieved due to operational challenges (Diesel). Specification for costruction of wingwalls submitted to SCM for appoitnemnet of service provider | N/A | Construction of 16 culverts and 8 wingwall | Construction of 08 culverts and 10 wingwalls | R 500 000.00 | Photographs, Ward Councillors confirmation letter | Technical services
BSID 32 | Road Maintenance Materials | Purchase | Improve maintenance capacity | BLM | Number set of identified road maintenance materials purchased by June 2024 | 4 sets of identified road maintenance materials purchased by June 2023(Wheel barrows(05),Brooms(30),square shovels(10) and digging spades(10) | 4 sets of identified road maintenance materials purchased by June 2024(Wheel barrows(05),Brooms(30),square shovels(10) and digging spades(10) | Specification and SCM processes | 4 sets of identified road maintenance materials purchased(Wheel barrows(05),Brooms(30),square shovels(10) and digging spades(10)) | Target Achieved. 4 sets of identified road maintenance materials purchased(Wheel barrows(05),Brooms(30),square shovels(10) and digging spades(10)) | N/A | N/A | N/A | N/A | R 100 000 | Proof of purchase | Technical services
BSID 37 | Construction of Danzig Creche | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To provide safe and sustainable educational facility services | Danzig | Percentage construction of Danzig Creche Completed by September 2023 | Appointment of contractor, Site handover,Site setablishment,Foundations, Drilling of borehole, Brickwork Super structure upto wall plate level completed | 100% construction of Danzig Creche Completed by September 2023 (100% construction of Superstructure with roofing,fencing,Kids play ground. Drilling of borehole and septic tank | 100% construction of Danzig Creche Completed by September 2023 (100% construction of Superstructure with roofing,fencing,Kids play ground. Drilling of borehole and septic tank) | N/A | N/A | N/A | N/A | N/A | N/A | R1,051,332 | Advert,appointment letters,handover minutes,Site visit report ,pictures and Completion certicate | Technical services
BSID 38 | Construction of Mongalo Creche | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To provide safe and sustainable educational facility services | Mongalo | Percentage construction of Mongalo Creche Completed by September 2023 | Appointment of contractor, Site handover,Site setablishment,Foundations, Drilling of borehole, Brickwork Super structure upto wall plate level completed | 100% construction of Mongalo Creche Completed by September 2023 (100% construction of Superstructure with roofing,fencing,Kids play ground. Drilling of borehole and septic tank) | 100% construction of Mongalo Creche Completed by September 2023 (100% construction of Superstructure with roofing,fencing,Kids play ground. Drilling of borehole and septic tank) | N/A | N/A | N/A | N/A | N/A | N/A | 992.289 | Advert,appointment letters,handover minutes,Site visit report ,pictures and Completion certicate | Technical services
BSID 40 | Construction of Mochemi access and internal streets | Confirmation of the Project on the IDP, Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To ensure availabity of infrastructure to support public transport | Mochemi | Kilometres of Roadbed layer, Sub base and base layer for Mochemi access road and internal street completed by June 2024 | New Indicator | Construction of 6,2 Km of Roadbed layer, Sub base and base layer for Mochemi access road and internal street completed by June 2024 | Tender Stage, Site Handover and Establishment | CONSTRUCTION STAGE – Site clearance and road excavations | Target Achieved: CONSTRUCTION STAGE – Site clearance and road excavations | None | None | CONSTRUCTION STAGE relocations of existing services, construction of road bed for Lethaleng to Pickum access road | 100% construction of Sub-base and base layerworks for Mochemi access road and internal street completed bu June 2024 | R 24,000,000,00 | Advert,appointment letters,handover minutes,Site visit report ,pictures | Technical services
BSID 41 | Construction of Lethaleng to Pickum access road | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To ensure availabity of infrastructure to support public transport | Lethaleng and Pickum | Kilometres of Roadbed layer and Sub base and base layer for Lethaleng to Pickum access road completed by June 2024 | New Indicator | Construction of 6,2 km of Roadbed layer and Sub base and base layer for Lethaleng to Pickum access road completed by June 2024 | Tender Stage, Site Handover and Establishment | CONSTRUCTION STAGE – Site clearance and road excavations | Target Achieved: CONSTRUCTION STAGE – Site clearance and road excavations | N/A | N/A | CONSTRUCTION STAGE relocations of existing services, construction of road bed for Lethaleng to Pickum access road | 100% construction of Sub-base and base layerworks for Lethaleng to Pickum access road completed bu June 2024 | R 26,531,379 | Advert,appointment letters,handover minutes,Site visit report ,pictures | Technical services
BSID 49 | Upgrading of Tolwe Satellite office | Appointment of service provider and construction | To improve office space | Tolwe | Percentage upgrading of Tolwe satellite office by June 2024 | New indicator | 100% upgrading of Tolwe satellite office by June 2024 | 100% upgrading of Tolwe satellite office | 100% upgrading of Tolwe satellite office | Target not achieved | Delays in SCM processes | Fast track appointment of the service provider with SCM | N/A | N/A | R200 000.00 | Reports | Community Services
BSID 52 | Indigent relief | Provision of indigent services | To provide indigent relief | BLM | Number Indigent register updated by June 2024 | .5340 Indigent provided with Free basic electricity | 1 x Indigent register updated by June 2024 | N/A | N/A | N/A | N/A | N/A | N/A | 1 x indigent register updated by June 2024 | OPEX | Updated Indigent Register | Budget & Treasury
INSTITUTIONAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
NDP | BUILDING CAPABLE AND DEVELOPMENTAL STATE
OUTCOME 9 |  | ADMINISTRATIVE AND FINANCIAL CAPABILITY
Project Details
Project/KPI Number | Project Name | Project Description (major activities) | Strategic Objective | Location | Key Performance Indicator | 2022-23 Baseline | 2023-24 Annual Target | Quarterly Projections | [6 empty] | 2023-24 Budget | Portfolio of evidence | Responsible Department
[8 empty] | Q1 | Q2 | Q2 Actual Performance | Reason for variance | Corrective Measure | Q3 | Q4
MTOD 01 | Fleet Management | purchase | improved fleet management | BLM | Number Tracker and Chassis purchased by June 2024 | 3X Graders | 1 Tracker and 1 Chassis purchased by June 2024 | Specification and SCM processes | 1 Tracker and 1 Chassis purchased | Target not Achieved. | Immediate need for 4 bakkies in electrical unit and three sedans for traffic unit | Proposal for adjustment of target. | N/A | N/A | R 7 600 000 | Proof of purchase. Photos | Corporate services
MTOD 04 | Wi-Fi Installation | Installation of Wi-Fi at all Municipal Offices. | Harmonize connectivity | BLM | Installation of devices that enables wifi connection at Municipal Offices | All municipal offices to have internet connection. | All municipal offices to have internet connection. | Installation of devices. | N/A | Target not achieved. Devices were only installed in the main office | Installation delays on the part of service provider | Meeting to be held with service provider by end of January 2024 | N/A | N/A | R 400 000 |  | Corporate services
MTOD 09 | Training for councillors | conduct councilors training | To improve skills and maximize productivity | BLM | Number councillors trained by June 2024 | Training of councillors |  | Appointment of services providers | 15 councillors to be trained. | Target not Achieved Appoitment of Service providers ntot done and Only councilors were trained | Government institurions will reopen in the 03rd quarter | Revision of the target t be completed in the 03rd quarter | 07 Councillors to be trained. | N/A | R 500 000.00 | Report | Corporate services
MTOD 10 | Training for officials & Interns | conduct employees training | to improve skills and maximize productivity | BLM | Number of employees trained by June 2024 | 31 Employees trained by June 2023 | 31 Employees trained by June 2024 | Appointment of service providers. | 20 Employees trained | Target not achieved. Serrvice providers not appointed and Only 3 employees are currently enrolled for CPMD with the university of Witwatersrand | Most identified isntitutins can only accommodate potential trainees from the 03rd quarter | Revision of the target t be completed in the 03rd quarter | 11 Employees to be trained. | N/A | R 400 000 | Report | Corporate services
MTOD 11 | Municipal employees bursaries | Support to employees | To improve skills and maximize productivity | BLM | Numbers report on employees bursary compiled by June 2024 | 2022 Bursary scheme | One report on employees bursary compiled by June 2024 | N/A | N/A | N/A | N/A | N/A | One report on employees bursary compiled | N/A | R 300 000 | Report | Corporate services
MTOD 15 | Employee wellness | Conducting employee wellness | improve employees health and well-being, optimize perfomance and productivity | BLM | Number reports on the employee wellness programme compiled by June 2024 | Two Reports on employee wellness conducted | Two Reports on employee wellness programme compiled by June 2024 | Employee wellness | Employee wellness | Target Achieved. The Emplloyee wellness was held on the 03rd August 2023 and 13th December 2024 | N/A | N/A | N/A | Employee wellness | R 98 000.00 | Report and attendance registers | Corporate services
MTOD 16 | Uniform and protective clothing | Purchasing of Uniform and protective clothing | To protect employees from exposure to work place hazards and the risk of injuries | BLM | Number of employees provided with protective clothing by June 2024 | 90 employees provided with PPE | 90 employees provided with protective clothing by June 2024 | Appointment of services provider | 90 employees provided with protective clothing. | Target not achieved. The service provider was appointed on a two year contract but protective clothing for the current financial year is yet to be delivered | Delay in delivery on the part of the service provider | Protective clothing to be delivered during the third quarter | N/A | N/A | R 700 000 | Collection register | Corporate services
MTOD18 | Conduct waste disposal facilities external audits | Conduct external Audits | To ensure efficient Waste Management | BLM | Number waste disposal facilities external audits conducted by June 2024 | New Indicator | 01 waste disposal facilities external audit conducted by June 2024 | N/A | N/A | N/A | N/A | N/A | 01 waste disposal facilities external audits conducted | N/A | R 200 000 | Report | Community Services
MTOD 20 | Procurement of household wheelie bins | Procurement | To ensure efficient Waste Management | BLM | 300 wheelie bins procured by June 2024 | New Indicator | 300 wheelie bins procured by June 2024 | 300 wheelie bins procured | N/A | Target not achieved | Delays in SCM processes. | Tofastrack procurement of 300 wheele bins through SCM | N/A | N/A | R 400 000 | Report | Community Services
MTOD22 | Conduct Cleaning Campaigns | Facilitation of Cleaning Awareness and Campains | To ensure awareness on waste management | BLM | Number of cleaning campaigns conducted by June 2024 | 04 cleaning campaigns conducted | 04 cleaning campaigns conducted by June 2024 | 01 cleaning campaigns conducted | 01 cleaning campaigns conducted | Target Achieved. 02 cleaning campaigns conducted Achieved | N\A | N\A | 01 cleaning campaigns conducted | 01 cleaning campaigns conducted | R 50 000 | Reports and photos | Community Services
MTOD23 | Sign boards, notices and flyers | Procurement | To ensure compliance on waste management | BLM | Number of sign boards, notices and flyers procured by June 2024 | New Indicator | 20 sign boards, 10 notices and 100 flyers procured by June 2024 | Needs and priorities assessments | Specifications compiled | Target Not Achieved | Delays in SCM Processes | To be procured in the 4rth quarter | SCM procurement | 20 Sign boards, 10 notices and 100 flyers procured | OPEX | Proopf of purchase | Community Services
MTOD24 | Landfill maintenance | Maintenance of landfill sites | To ensure proper maintenance and operation of site | BLM | Number landfill site maintenance reports compiled by June 2024 | 12 landfill site maintenance reports compiled | 12 landfill site maintenance reports compiled by June 2024 | 3 landfill site maintenance reports compiled | 3 landfill site maintenance reports compiled | Target Achieved. 6 landfill site maintenance reports compiled | N\A | N\A | 3 landfill site maintenance reports compiled | 3 landfill site maintenance reports compiled | R 4 900 000.00 | Reports | Community Services
MTOD 30 | Climate Change mitigation | purchase | Promote environmental management | BLM | 100 Trees purchased by June 2024 | New Indicator | 100 Trees purchased by June 2024 | 100 Trees purchased | 100 Trees Purchased | Target not Achieved. 100 trees purchased | Delays in SCM processes | Fastrack procurement processes with SCM | N/A | N/A | R 100 000 | Report | Community Services
MTOD31 | Procurement of cemetery record books | Procurement | To ensure that grave sites are registered | BLM | Number Cemetery record books purchased by June 2024 | 05 cemetery records books procured | 05 Cemetery record books procured by June 2024 | N/A | 05 cemetery records books procured | Target Not Achieved | Delays in SCM processes | Fastrack procurement processes with SCM | N/A | N/A | R 50 000.00 | Proopf of purchase | Community Services
MTOD 36 | Calibration of speed machines | Calibration and reporting | Maintenance | BLM | Number Maintenance Report compiled by June 2024 | 4 Maintenance Report compiled by June 2023 | 4 Maintenance Report compiled by June 2024 | 1 Maintenance Report compiled | 1 Maintenance Report compiled | Target Achieved. 02 maitenance reports compiled | N/A | N/A | 1 Maintenance Report compiled | 1 Maintenance Report compiled | R 77 500.00 | Reports | Community Services
MTOD 37 | Procurement of stationery | purchase | To ensure enough material for Traffic services | BLM | Percentage traffic stationery purchased by June 2024 | 100% Percentage traffic stationery purchased by June 2023 | 100% Percentage traffic stationery purchased by June 2024 | N/A | 100% Percentage traffic stationery purchased | Target Not Achieved | SCM Delays Specifications submitted to SCM. Still waiting for response | Fastrack procurement processes with SCM | N/A | N/A | R 50 000.00 | Proof of purchase | Community Services
MTOD 38 | Catering for four awareness's | Coordinate awareness campaigns | To celebrate transport month and promote awareness | BLM | Number transport Awareness Events conducted by June 2024 | 2 transport Awareness Event conducted by June 2023 | 4 transport Awareness Events conducted by June 2024 | 1 transport Awareness Event conducted | 1 transport Awareness Event conducted | Target Achieved. 02 transport Awareness Event conducted Achieved | N/A | N/A | 1 transport Awareness Event conducted | 1 transport Awareness Event conducted | R 50 000.00 | Reports | Community Services
MTOD 39 | Maintenance of equipment | Maintenance | To ensure proper working equipment | BLM | Number VTS machines calibrated by June 2024 | One VTS machines calibrated by June 2023 | One VTS machines calibrated by June 2024 | N/A | N/A | N/A | N/A | N/A | One VTS machines calibrated | N/A | R 77 500.00 | Report | Community Services
MTOD 41 | Pound Awareness campaigns | campaigns | Promote safety | BLM | Number awareness campaigns conducted by June 2024 | 4 awareness campaigns conducted by June 2023 | 4 awareness campaigns conducted by June 2024 | 1 awareness campaigns conducted | 1 awareness campaigns conducted | Target Achieved. 2 awareness campaigns conducted | N/A | N/A | 1 awareness campaigns conducted | 1 awareness campaigns conducted | R 50 000.00 | Reports | Community Services
MTOD 42 | Protective Clothing | purchase | Availability of PPE | BLM | Number set of uniform purchased for Law Enforcement Personnel by June 2024 | New Indicator | 10 sets of uniform purchased for Law Enforcement Personnel by June 2024 | Specification and SCM processes | 10 sets of uniform purchased for Law Enforcement Personnel | Target Not Achieved | Delays in Specifications submitted to SCM. Still waiting for response | Fast track purchase of PPE with SCM | N/A | N/A | R 200 000.00 | Proof of purchase | Community Services
MTOD45 | Maintenance of buildings | Maintenance | To ensure safe Municipal facilities | BLM | Number municipal buildings maintained by June 2024 | 3 municipal buildings maintained by June 2023 | 7 municipal buildings maintained by June 2024 | Assessment | Specifications compiled and procurement | Target Achieved. Assessment , specification and procurement done | N/A | N/A | 7 municipal buildings maintained. | N/A | R 300 000 | Reports | Community Services
MTOD46 | Maintenance of Sports facilities | Maintenance | To ensure user-friendly Sports facilities | BLM | Number sports facilities maintained by June 2024 | 2 sports facilities maintained by June 2023 | 3 sports facilities maintained by June 2024 | Assessment | Specification and procurement | Targt Not Achieved | Delays in SCM Prcesses. Specifications submitted to SCM. Still waiting for response | To fast track the SCM processes | 3 sports facilities maintained | N/A | R200 000 | Reports | Community Services
MTOD47 | Maintenance of Community halls | Maintenance | To ensure user-friendly Community Halls | BLM | Number community halls maintained by June 2024 | 2 community halls maintained by June 2024 | 6 community halls maintained by June 2024 | Assessment | Specification and procurement | Target Not Achieved | Delays in SCMprcesses Specifications submitted to SCM. | To fast track the SCM processes | 6 community halls maintained | N/A | R100 000 | Reports | Community Services
MTOD 48 | Purchase of disaster relief matertial | purchase | To ensure disaster preparedness | BLM | Number relief material procured, i.e. 10 tents, 10 school uniforms, 50 blankets, 50 mattresses purchased by June 2024 | New Indicator | 120 relief material procured, i.e. 10 tents, 10 school uniforms, 50 blankets, 50 mattresses purchased by June 2024 | 120 relief material procured, i.e. 10 tents, 10 school uniforms, 50 blankets, 50 mattresses purchased | N/A | N/A | Specifications submitted to SCM | To fast track the SCM processes | N/A | N/A | R 300 000 | Reports | Community Services
MTOD49 | Conduct Disaster Management education and awareness campaigns to communities | campaigns | To unsure effective Disaster Management | BLM | Number disaster education and awareness campaigns conducted by June 2024 | 4 Education and awareness campaigns conducted by June 2023 | 4 disaster Education and awareness campaigns conducted by June 2024 | 1 Disaster Education and awareness campaigns conducted | 1 Disaster Education and awareness campaigns conducted | Target Achieved1 Disaster Education and awareness campaigns conducted | N/A | N/A | 1 Disaster Education and awareness campaigns conducted | 1 Disaster Education and awareness campaigns conducted | R50 000.00 | Reports | Community Services
MTOD 51 | IDP Steering Committees and Review Sessions | Compilation of quarterly SDBIP Reports | Compliance with legislations | BLM | Number of SDBIP Reports compiled by June 2024 | Four SDBIP Reports compiled by June 2023 | Four SDBIP Reports compiled by June 2024 | Fourth Quarter SDBIP 2022-23 | First Quarter SDBIP Report 2023/24 | Target Achieved Fourth Quarter and 01st Quarter SDBIP report compiled | N/A | N/A | Mid-year Quarter SDBIP Report 2023/23 | Third Quarter SDBIP Report 2023/24 | R 540 000.00 | Reports | MM/Mayor’ Office
MTOD 52 | Performance Assessments | Conducting individual performance Assessments | Enhanced Municipal performance | BLM | Number individual performance assessments conducted(Annual and mid-year) by June 2024 | Two Individual Assessments conducted(Annual and Mid-year) by June 2023 | Two Individual Assessments conducted(Annual and Mid-year) by June 2024 | N/A | N/A | N/A | N/A | N/A | Annual and Mid-year Individual Assessments conducted | N/A | R10 000.00 | Reports and Registers | MM/Mayor’ Office
MTOD 53 | Security Management | Appointment and payment of Physical Security service provider | Secure municipal property | BLM | Number Physical security services reports compiled by June 2024 | 12 Physical security services reports compiled by June 2023 | 12 Physical security services reports compiled by June 2024 | 3 Physical security services reports compiled | 3 Physical security services reports compiled | Target Achieved. 06 Pysical Security services reports compiled | N/A | N/A | 3 Physical security services reports compiled | 3 Physical security services reports compiled | R 18 000 000 | Reports | MM/Mayor’ Office
MTOD 54 | Security cameras | Appointment of service provider and installation of camera system | Secure municipal property | BLM | Percentage new camtera system installed by June 2024 | New Indicator | 100% installation new camera system by June 2024 | Assessment and design report | 100% installation new camera system by June 2024 | Target Not Achieved | Delays in SCM processes | To fast track the SCM processes | N/A | N/A | R 300 000 | Reports | MM/Mayor’ Office
MTOD 55 | Access control | Appointment of service provider and installation of access control | Secure municipal property | BLM | Percentage new access system installed by June 2024 | New Indicator | Percentage installation access control system by June 2024 | Assessment and design report | 100% installation access control system by June 2024 | Target Not Achieved | Delays in SCM processes | To fast track the SCM processes | N/A | N/A | R 1 000 000.00 | Reports | MM/Mayor’ Office
MTOD 56 | Gazetting of By-laws | Gazetting | Strengthen municipal legal services | BLM | Number by-laws gazetted by June 2024 | Three by-laws gazetted by June 2023 | Five by-laws gazetted by June 2024 | Five by-laws gazetted | N/A | N/A | N/A | N/A | N/A | N/A | R 150 000 | Report | Corporate services
MTOD 57 | Contract Management | Reports | Strengthen municipal legal services | BLM | Number contract management reports compiled by June 2024 | Four contract management reports compiled by June 2023 | Four contract management reports compiled by June 2024 | One contract management reports compiled | One contract management reports compiled | Target Achieved. One Contract Managemnent report Compiled | N/A | N/A | One contract management reports compiled | One contract management reports compiled | OPEX | Reports | Corporate services
MTOD 58 | Litigations | Compilation of reports | Strengthen municipal legal services | BLM | Number litigation reports compiled by June 2024 | Four litigation reports compiled by June 2023 | Four litigation reports compiled by June 2024 | One litigation report compiled | One litigation report compiled | Target Achieved One litigation report compiled | N/A | N/A | One litigation report compiled | One litigation report compiled | R 3 000 000 | Reports | Corporate services
LOCAL ECONOMIC DEVELOPMENT
OUTCOME 9 |  | IMPLEMENTATION OF COMMUNITY WORKS PROGRAMME
Project Details
Project/KPI Number | Project Name | Project Description (major activities) | Strategic Objective | Location | Key Performance Indicator | 2022/23 Baseline | 2023-24 Annual Target | Quarterly Projections | [6 empty] | 2023-24 Budget | Portfolio of evidence | Responsible Department
[8 empty] | Q1 | Q2 | Q2 Actual Performance | Reason for variance | Corrective Measure | Q3 | Q4
LED 01(1) | LED Projects | Financial support to LED Projects | To create and promote LED initiatives in the business sector | BLM | Number LED Projects Financially supported by June 2024 | 3 projects supported financially | 4 LED Projects Financially supported by June 2024 | Identification of SMMEs to be supported | facilitate the apointment process of service provider | Target not Achieved. Identificatin of SMME to be supported done but appointmentf servicproviders still mot done | Delays in SCM processes | To continue making follow ups with SCM for appointment of service provider | 3 LED Projects Financially supported | Project close out report | R 600 000.00 | Reports and pictures | Economic Development & Planning
LED 1(2) | LED Summit | Coordination of a summit | To create and promote LED initiatives in the business sector | BLM | Number LED summit held by June 2024 |  | One LED summit held by June 2024 | N/A | One LED summit held by June 2024 | Target Achieved. LED submit held on the 23rd November 2023 | N/A | N/A | N/A | N/A | R 300 000 | Reports and Attendance Register | Economic Development & Planning
LED 03 | Informal traders | management of hawkers | To create and promote LED initiatives in the business sector | BLM | Number quarterly reports on managemnt of hawkers compiled by June 2024 | Four quarterly reports on managemnt of hawkers compiled by June 2024 | Four quarterly reports on managemnt of hawkers compiled by June 2024 | One quarterly report on managemnt of hawkers compiled | One quarterly report on managemnt of hawkers compiled | Target Achieved. 02 Quarterly report on management of hawkers compiled | N/A | N/A | One quarterly report on managemnt of hawkers compiled | One quarterly report on managemnt of hawkers compiled | OPEX | Reports | Economic Development & Planning
LED 04 | Informal Traders By-Law | Development of by-law | To create and promote LED initiatives in the business sector | New Indicator | Number by-law developed and approved by June 2024 | New Indicator | One by-law developed and approved by June 2024 | N/A | N/A | N/A | N/A | N/A | N/A | One by-law developed and approved by June 2024 | OPEX | By-law and Council resolution | Economic Development & Planning
LED 05 | EPWP - Grant | Appointment of EPWP PRACTIONERS | To create job opportunities through EPWP programme | BLM | Number job opportunities created through EPWP programme by June 2024 | 235 opportunities created by June 2023 | 250 job opportunities created through EPWP programme by June 2024 | 250 EPWP job opportunities created | N/A | N/A | N/A | N/A | N/A | N/A | R 5 300 040 | List and reports | Community Services
FINANCIAL VIABILITY AND MANAGEMENT
NDP | BUILDING OF KEY CAPABILITIES(HUMAN,PHYSICAL &INSTITUTIONAL)
OUTCOME 9 |  | ADMINISTRATIVE AND FINANCIAL CAPABILITY (OUTPUT 6)
Project Details
Project/KPI Number | Project Name | Project Description (major activities) | Strategic Objective | Location | Key Performance Indicator | 2022-23 Baseline | 2023-24 Annual Target | Quarterly Projections | [6 empty] | 2023-24 Budget | Portfolio of evidence | Responsible Department
[8 empty] | Q1 | Q2 | Q2 Actual Performance | Reason for variance | Corrective Measure | Q3 | Q4
MFVM 01 | Annual financial statement | Compilation of AFS | Enhance Sound Municipal financial viability and management | BLM | Number set of AFS Compiled & submitted to AGSA,LPT,COGOHSTA& NT by June 2024 | 2020/21 AFS compiled & submitted to AGSA, LPT& NT | One set of AFS Compiled & submitted to AGSA,LPT,COGOHSTA& NT by June 2024 | AFS Compiled & submitted to AGSA,LPT,COGOHSTA& NT by June 2024 | N/A | N/A | N/A | N/A | N/A | N/A | R 950,000.00 | Acknowledgement of the receipt from AGSA, LPT, COHGSTA & NT | Budget & Treasury
MFVM 02 | Quarterly mSCOA data strings report | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | Number Quarterly mSCOA data strings report compiled by June 2024 | 4 Quarterly mSCOA data strings report compiled by June 2023 | 4 Quarterly mSCOA data strings report compiled by June 2024 | 1 Quarterly mSCOA data strings report compile | 1 Quarterly mSCOA data strings report compile | Target Achieved. 02 Quarterly MSCOA data strings report compiled | N/A | N/A | 1 Quarterly mSCOA data strings report compile | 1 Quarterly mSCOA data strings report compile | OPEX | Reports | Budget & Treasury
MFVM 03 | Monthly budget statement(Sec 71 reports) | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | 12 monthly budget statements submitted to Treasury within 10 working days after month-end | 12 monthly budget statements submitted to Treasury within 10 working days after month-end | 12 monthly budget statements submitted to Treasury within 10 working days after month-end | 3 monthly budget statements submitted to Treasury within 10 working days after month-end | 3 monthly budget statements submitted to Treasury within 10 working days after month-end | Target Achieved. 06 monthly budget statements submitted to Treasury within 10 working days after month-end | N/A | N/A | 3 monthly budget statements submitted to Treasury within 10 working days after month-end | 3 monthly budget statements submitted to Treasury within 10 working days after month-end | OPEX | Reports | Budget & Treasury
MFVM 04 | Quarterly mSCOA data strings report | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | Number Quarterly mSCOA data strings report compiled by June 2024 | 4 Quarterly mSCOA data strings report compiled by June 2023 | 4 Quarterly mSCOA data strings report compiled by June 2024 | 1 Quarterly mSCOA data strings report compile | 1 Quarterly mSCOA data strings report compile | Target Achieved. 02 Quarterly mSCOA data strings report compile | N/A | N/A | 1 Quarterly mSCOA data strings report compile | 1 Quarterly mSCOA data strings report compile | OPEX | Reports | Budget & Treasury
MFVM 05 | MSCOA projects implementation | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | Number MSCOA projects implementation reports compiled by June 2024 2023 | One MSCOA projects implementation reports compiled by June 2023 | 4 x MSCOA projects implementation reports compiled by June 2024 | 1 x MSCOA projects implementation reports compiled | 1 x MSCOA projects implementation reports compiled | Target Achieved. 02 MSCOA projects implemnetation reprts compiled | N/A | N/A | 1 x MSCOA projects implementation reports compiled | 1 x MSCOA projects implementation reports compiled | OPEX | Project Reports | Budget & Treasury
MFVM 06 | Reconciliations and registers | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | Number monthly reconciliation, registers and schedules compiled by June 2024 | 12 monthly reconciliation and registers reported to portfolio by June 2023 | 400 x monthly reconciliation, registers and schedules compiled by June 2024 | 100 x monthly reconciliation, registers and schedules compiled by Sept 2023 | 100 x monthly reconciliation, registers and schedules compiled by Dec 2023 | Target Achieved. 200 x monthly reconciliation, registers and schedules compiled by December 2023 | N/A | N/A | 100 x monthly reconciliation, registers and schedules compiled by March 2024 | 100 x monthly reconciliation, registers and schedules compiled by June 2024 | OPEX | Reconciliation, registers and schedules compiled/performed | Budget & Treasury
MFVM 07 | Annual Budget (Draft) | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | Number draft budget compiled and tabled by June 2024 | 1 draft budget compiled & tabled by June 2023 | 1 x draft budget compiled and tabled by March 2024 | N/A | N/A | N/A | N/A | N/A | 1 x draft budget compiled and tabled March | N/A | OPEX | Council Resolution | Budget & Treasury
MFVM 08 | Annual Budget (Final) | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | Number final budget compiled by June 2024 | 1 Final budget compiled by June 2023 | 1 x Final budget compiled by June 2024 | N/A | N/A | N/A | N/A | N/A | N/A | 1 x Final budget compiled | OPEX | Council Resolution | Budget & Treasury
MFVM 09 | Adjustment budget | Compilation of adjustment budget | Enhance Sound Municipal financial viability and management | BLM | Number adjustment budget compiled by June 2024 | Adjustment budget compiled | 1 x adjustment budget compiled and submitted to council, LP & NT by June 2024 | N/A | N/A | N/A | N/A | N/A | 1 x adjustment budget compiled and submitted to LP & NT | N/A | OPEX | Council resolution | Budget & Treasury
MFVM 12 | Compile financial report, (section 52) | Compilation of report | Enhance Sound Municipal financial viability and management | BLM | Number quarterly financial reports compiled and reported to Executive Committee(EXCO) and Council by June 2024 | 4 x quarterly financial report compiled and reported to EXCO & Council by June 2023 | 4 x quarterly financial report compiled and reported to Executive committee and Council by June 2024 | 1 x quarterly financial report compiled and reported to EXCO & Council | 1 x quarterly financial report compiled and reported to EXCO & Council | Target Achieved. 2 x quarterly financial report compiled and reported to EXCO & Council | N/A | N/A | 1 x quarterly financial report compiled and reported to EXCO & Council | 1 x quarterly financial report compiled and reported to EXCO & Council | OPEX | Reports | Budget & Treasury
MFVM 13 | Procurement plan | Compilation of report | Enhance Sound Municipal financial viability and management | BLM | Number procurement plan developed and approved by June 2024 | 1 x procurement plan developed and approved | 1 x procurement plan developed and approved by June 2024 | 1 procurement plan developed and approved | N/A | N/A | N/A | N/A | N/A | N/A | OPEX | Procurement plan | Budget & Treasury
MFVM 15 | Conduct training of SCM practitioner | Conduct training of SCM practitioner | Enhance Sound Municipal financial viability and management | BLM | Number SCM Training attended by June 2024 | SCM Training attended | 1 x SCM Training conducted by June 2024 | N/A | N/A | N/A | N/A | N/A | 1 x SCM Training attended | N/A | R 200,000.00 | Attendance Register | Budget & Treasury
MFVM 16 | Acquisition management(Bids Register) | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | Number updated awarded Bids reports by June 2024 | 12 x updated awarded Bids reports by June 2024 | 4 x updated awarded Bids placed on website by June 2024 | 1 x updated list awarded Bids placed on website | 1 x updated list awarded Bids placed on website | Target Achieved. 2 x updated list awarded Bids placed on website | N/A | N/A | 1 x updated list awarded Bids placed on website | 1 x updated list awarded Bids placed on website | OPEX | List of awarded Bids (updated) | Budget & Treasury
MFVM 17 | Revenue management committee | Revenue management committee meetings to be held | Enhance Sound Municipal financial viability and management | BLM | Number revenue management meetings held by June 2024 | Two revenue management meetings held | 4 x revenue management meetings to be held by June 2024 | 1 x revenue management meeting to be held | 1 x revenue management meeting to be held | Target not Achieved. | N/A | N/A | 1 x revenue management meeting to be held | 1 x revenue management meeting to be held | OPEX | Attendance Register | Budget & Treasury
MFVM 28 | Unbundling of Asset Register | Unbundling of Asset Register | Enhance Sound Municipal financial viability and management | BLM | Number unbundling of assets report compiled by June 2024 | Asset unbundling reports | 1 x unbundling of assets report compiled by June 2024 | 1 x Report on asset Unbundling | N/A | N/A | N/A | N/A | N/A | N/A | R 1 100 000 | Unbundling of Asset report | Budget & Treasury
MFVM 29 | Insurance of Municipal assets | Insurance of Municipal Assets | Improve asset lifespan | BLM | Number insurance policy / agreement signed by June 2024 | Number of insurance policy / agreement signed | 1 x insurance policy / agreement signed by June 2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | R2 000,000.00 | Signed Insurance Policy | Budget & Treasury
MFVM 30 | Reporting of incidents occurred | Reports | Enhance Sound Municipal financial viability and management | BLM | Number incidents reports compiled by June 2024 | 12 monthly incidents reports compiled by June 2023 | 12 monthly incidents reports compiled by June 2024 | 1 x incidents report compiled | 1 x incidents report compiled | Target Achieved. 2x Incident reprts compiled | N/A | N/A | 1 x incidents report compiled | 1 x incidents report compiled | OPEX | Incidents Reports | Budget & Treasury
GOOD GOVERNANCE AND PUBLIC PARTICIPATION
NDP | ACTIVE ENGAGEMENT OF CITIZENS IN THEIR OWN DEVELOPMENT
OUTCOME 9 | DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL(OUTPUT 5)
Project Details
Project/KPI Number | Project Name | Project Description (major activities) | Strategic Objective | Location | Key Performance Indicator | 2022-23 Baseline | 2023-24 Annual Target | Quarterly Projections | [6 empty] | 2023-24 Budget | Portfolio of evidence | Responsible Department
[8 empty] | Q1 | Q2 | Q2 Actual Performance | Reason for variance | Corrective Measure | Q3 | Q4
GGPP 01 | Auditing | Coordination of external Audit process | Improved audit opinion | BLM | Number unqualified audit opinion obtained for 2022-23 financial year by June 2024 | Unqualified audit opinion obtained for 2021-22 | One unqualified audit opinion obtained for 2022-23 financial year by June 2024 | N/A | One unqualified audit opinion obtained for 2022-23 financial year | Target Not Achieved. Received qualified opinion | Issues related to Assets raised in AG's Management report | To adress raised issues in the Audit Action Plan | N/A | N/A | R 5 000 000 | Audit report | MM/Mayor’ Office
GGPP 02 | Audit & Risk Committee Allowances | Coordination of Risk and Audit Committee meetings | Improved audit opinion | BLM | Number Risk and Audit Committee meetings by June 2024 | 08 meetings held by June 2023 | 04 Risk and 04 Audit Committee meetings by June 2024 | 01 Risk and 01 Audit Committee | 01 Risk and 01 Audit Committee | Target Achieved. 02 Risk were held on the 13th July and the 16th October and 02 Audit Committee held on the 13th July, 25th October 2023 | N/A | N/A | 01 Risk and 01 Audit Committee | 01 Risk and 01 Audit Committee | R 773 000 | Minutes and Registers | MM/Mayor’ Office
GGPP 03 | Printing and Publication | Production of Municipal newsletter,diaries,calendars | To improve communication | BLM | Number newsletter editions,diaries and calendars produced by June 2024 | 2 editions newsletters, 100 diaries and 1000 calendars produced by June 2023 | 2 newsletter editions, 60 diaries and 2000 calendars produced by June 2024 | N/A | One newsletter edition produced | Target Not Achieved | Late issuance of order. Service provider now busy with the graphics and design work. | Service providers to be met and requested to speed up the work. | 60 dairies and 2000 calendar produced | One newsletter edition produced | R 400 000 | Copy of newletter, Reports and PoP | Corporate services
GGPP 04 | Publicity and Branding | procurement of banners and gazebos | Enhanced communication | BLM | Number banners and gazebos procured by June 2024 | 40 banners and 4 gazebos procured by June 2023 | 20 banners and 2 gazebos procured by June 2024 | 20 banners and 2 gazebos procured | N/A | N/A | N/A | N/A | N/A | N/A | R 300 000.00 | POP and delivery notes | Corporate services
GGPP 08 | Community Participation | Meetings | Enhanced Community participation | BLM | Number Council outreach programmes coordinated and supported by June 2024 | 6 Council outreach programmes coordinated and supported by June 2023 | 6 Council outreach programmes coordinated and supported by June 2024 | 1 Council outreach programmes coordinated and supported | 1 Council outreach programmes coordinated and supported | Target Target achieved. Two outreach programmes were held on the 28/07/2023 and 30/10/2023. | N/A | N/A | 2 Council outreach programmes coordinated and supported | 2 Council outreach programmes coordinated and supported | R 1 000 000 | Report | Corporate services
GGPP 09 | Whippery Management | Meetings | Promote multiparty relations | BLM | Number Whippery management meeting coordinated and supported by June 2024 | 4 Whippery management meeting coordinated and supported by June 2023 | 4 Whippery management meeting coordinated and supported by June 2024 | 1 Whippery management meeting coordinated and supported | 1 Whippery management meeting coordinated and supported | Target achieved. Whippery Management meetings were held on the 27/07/2023 and 27/10/2023 | N/A | N/A | 1 Whippery management meeting coordinated and supported | 1 Whippery management meeting coordinated and supported | 200000 | Report | Corporate services
GGPP 10 | MPAC Programmes | Coordination of MPAC programmes | To improve public participation | BLM | Number MPAC programs coordinated by June 2024 | 5 programmes coordinated by June 2023 | 5 MPAC programs coordinated by June 2024 | N/A | N/A | N/A | N/A | N/A | 5 Coordination of MPAC programs coordinated by June 2023 | N/A | R 790 000 | Report | Corporate services
GGPP 11 | Ward Committees’ Conference Programmes | Coordination and support | To improve public participation | BLM | Number Ward committee conference held by June 2024 | Cluster conferences conducted | 01 Ward committee conference held by June 2024 | N/A | N/A | N/A | N/A | N/A | 01 Ward committee conference | N/A | R1,900 000 | Report | Corporate services
GGPP 12 | Remuneration of ward committees | Payment of stipends for Ward Committees | To improve public participation | BLM | Number Ward Committee members receiving monthly stipend by June 2024 | 220 Ward Committee members receiving monthly stipend | 220 Ward Committee members receiving monthly stipend by June 2024 | 220 Ward Committee members receiving monthly stipend | 220 Ward Committee members receiving monthly stipend | Target achieved. All 440 ward committees received their monthly stipends | N/A | N/A | 220 Ward Committee members receiving monthly stipend | 220 Ward Committee members receiving monthly stipend | R4,500 000.00 | Report | Corporate services
GGPP 13 | Council support literature | Printing of Booklets | Pocket books to assist Councillors with Rules and Orders. | BLM | Number of printed booklets. | Number of printed booklets. | 60 Rules of Order, 250 Ward Committees’ Constitution and 100 Service Delivery Charter booklets developed | Advertisement | Procurement of 60 Booklets | Target achieved. Advertiksemnet and Rules of Order, Ward Committees'Constitution as well as Service Delivery Charter booklets were procured | N/A | N/A | N/A | N/A | 200000 | Report | Corporate services
GGPP | Sports for employees |  | Promote employee welllness | BLM | Number sports Activity coordinated by June 2024 | One sports Activity coordinated by June 2023 | 01 Sports activity coordinated by June 2024 | N/A | 01 Activity coordinated | Target Achieved. 01Sports activity cordinated | N/A | N/A | N/A | N/A | R 1 200 000 | Reports | Corporate services
GGPP | Internet towers | appointment of service providers and installation of towers | To improve connnectivity | BLM | 03 internet towers installed | New indicator | 03 internet towers installed | N/A | 03 internet towers installed | Target not Achieved | The target is irrelevant to the department | The target to be relocated to MM's Office | N/A | N/A | R 1 500 000 | Reports | Corporate services
GGPP 14 | IDP Review | Review of IDP/Budget | To ensure successful review of the IDP | BLM | Number IDP/Budget reviewed compiled by June 2024 | IDP public participation report | One IDP/Budget reviewed compiled by June 2024 | N/A | N/A | N/A | N/A | N/A | N/A | One IDP/Budget reviewed compiled | OPEX | Copy of IDP and Council resolution | Economic Development and Planning
GGPP 15 | IDP/Budget Process plan | development and approval of plan | To ensure successful review of the IDP | BLM | Number IDP Process plan developed and approved by June 2024 | One IDP Process plan developed and approved by June 2023 | One IDP Process plan developed and approved by June 2024 | One IDP Process plan developed and approved by June 2024 | N/A | Target Achieved. 01Process Plan developed and approved | N/A | N/A | N/A | N/A | OPEX | Copy and Council Resolution | Economic Development and Planning
GGPP 16 | IDP/Budget Booklets | Produce Booklets | To ensure successful review of the IDP | BLM | Number IDP Booklets produced by June 2024 | New indicator | 50 IDP Booklets produced by June 2024 | IDP Booklets produced | N/A | N/A | N/A | N/A | N/A | N/A | R 200 000 | Proof of purchase | Economic Development and Planning
GGPP 17 | Strategic planning sessions | Hold sessions | To ensure successful review of the IDP | BLM | Number strategic sessions held by June 2024 | 2 Strategic session held by June 2023 | 6 Strategic session held by June 2024 | 1 Strategic session held | 2 Strategic session held | Target Achieved.03 Strategic Sessions held during the months of July and Octobr 2023 | N/A | N/A | 1 Strategic session held | 2 Strategic session held | R 650 000 | Report | Economic Development and Planning
GGPP 18 | IDP/Budget Public participation | IDP stakeholder consultations | To ensure effective public participation in the review of the IDP | BLM | Number IDP consultative meetings conducted, IDP consultative reports compiled by June 2024 | IDP public participation report | 13 IDP consultative meetings conducted and One IDP consultative reports compiled by June 2024 | N/A | 1 Rep forum | Target Achieved. 01 Rep Forum Held on the 16th November 2023 | N/A | N/A | N/A | 13 consultative meetings held | R 600 000 | Reports | Economic Development and Planning
GGPP 19 | Development municipal multi sectoral implementation plan | development and approval of plan | To Provide support on HIV/AIDS progra | BLM | Number Municipal HAST plan approved by the Local AIDS council and submitted to DAC and LPAC by June 2024 | One plan developed and submitted by 2023 | 1 Municipal HAST plan approved by the Local AIDS council and submitted to DAC and LPAC by June 2024 | 1 Municipal HAST plan approved by the Local AIDS council and submitted to DAC and LPAC | N/A | Target Achievced.1 Municipal HAST plan approved by the Local AIDS council and submitted to DAC and LPAC | N/A | N/A | N/A | N/A | OPEX | Reports | Community services
GGPP 20 | Conduct HIV/AIDS programmes | meetings | Implementation HIV/AIDS programmes | BLM | Number M&E meetings held by June 2024 | 2 HIV/AIDS programmes coordinated | 4 M&E meetings held by June 2024 | 1 M&E meetings held | 1 M&E meetings held | Target Achievced.2 M&E meetings held on the 26th October 2023 | N/A | N/A | 1 M&E meetings held | 1 M&E meetings held | OPEX | Reports | Community services
GGPP 21 | HIV/AIDS Council technical committee | meetings | Implementation HIV/AIDS programmes | BLM | Number AIDS Council technical committee meetings held by June 2024 | 2 HIV/AIDS programmes coordinated | 4 AIDS Council technical committee meetings held by June 2024 | 1 AIDS Council technical committee held | 1 AIDS Council technical committee held | Target Achieved 02 AIDS Council technical committee held on the 15th November 2023 | N/A | N/A | 1 AIDS Council technical committee held | 1 AIDS Council technical committee held | R 50 000 | Reports | Community services
GGPP 22 | Local Aids council meetings | meetings | Implementation HIV/AIDS programmes | BLM | Number Local Aids council meetings held by June 2024 | 4 Local Aids council meeting held by June 2023 | 4 Local Aids council meetings held by June 2024 | 1 Local Aids council meeting held | 1 Local Aids council meeting held | Target Achieved. 21 Local Aids council meeting held on the 13thh December 2023 | N/A | N/A | 1 Local Aids council meeting held | 1 Local Aids council meeting held | OPEX | Reports | Community services
GGPP 23 | Promote advocacy and stakeholder collaboration | establishment of committees | To Provide support on HIV/AIDS programme | BLM | Number HIV/AIDS ward committees established by June 2024 | 22 ward committees established by June 2023 | 22 ward committees established by June 2024 | 22 ward committees established | N/A | Target Achieved. 22 Ward Commitees established | N/A | N/A | N/A | N/A | OPEX | Report | Community services
GGPP 24 | HIV/AIDS Ward/Cluster meetings | meetings | Promote advocacy and stakeholder collaboration | BLM | Number HIV/AIDS ward/cluster meeting coordinated by June 2024 | 2 HIV/AIDS coordinated | 24 HIV/AIDS ward/cluster meeting coordinated by June 2024 | 6 HIV/AIDS ward/cluster meeting coordinated | 6 HIV/AIDS ward/cluster meeting coordinated | Target Achieved 12 HIV/AIDS ward/cluster meeting coordinated on the16th October and 01st November 2023 | N/A | N/A | 6 ward/cluster meeting coordinated | 6 ward/cluster meeting coordinated | R 100 000 | Reports | Community services
GGPP 25 | Prevent spread of communicable diseases | Hold awareness campaigns | To prevent spread of communicable diseases | BLM | Number HAST awareness campaigns and preventions held by June 2024 | 4 HAST awareness campaigns and preventions held by June 2023 | 4 HAST awareness campaigns and preventions held by June 2024 | 1 HAST awareness campaigns and preventions held | 1 HAST awareness campaigns and preventions held | Target Achieved 02 HAST awareness campaigns and preventions held on the 05th december 2023 | N/A | N/A | 1 HAST awareness campaigns and preventions held | 1 HAST awareness campaigns and preventions held | R 50 000 | Reports | Community services
GGPP 26 | Gender Programme | Support to gender programs | To provide support to special focus groups | BLM | Number men and women councils meeting coordinated by June 2024 | Two gender programs support to the gender programs | 4 men and 4 women councils meeting coordinated by June 2024 | 1 men and 1 women councils meeting coordinated | 1 men and 1 women councils meeting coordinated | Target Achieved. 2 men and 2 women councils meeting coordinated on the17th Nov 2023 | N/A | N/A | 1 men and 1 women councils meeting coordinated | 1 men and 1 women councils meeting coordinated | R 40 000 | Report and attendance registers | Community services
GGPP 27 | Special focus groupings and gender mainstreaming | cordination of events | promote the needs and interests of special focus groupings and gender mainstreaming | BLM | Number gender mainstreaming activities con ducted as per calendar events by June 2024 | Two gender programs supported by June 2023 | 4 gender mainstreaming activities con ducted as per calendar events by June 2024 | 1gender mainstreaming activities conducted as per calendar events | 1gender mainstreaming activities conducted as per calendar events | Target Achieved. 1gender mainstreaming activities conducted as per calendar events on the 27th ctober 2023 | N/A | N/A | 1gender mainstreaming activities conducted as per calendar events | 1gender mainstreaming activities conducted as per calendar events | R 40 000 | Reports | Community services
GGPP 28 | special focus groupings and gender mainstreaming(capacity building) | Conduct capacity building workshops | To provide support to disability and elderly groups | BLM | Number capacity building workshop conducted by June 2024 | 2 capacity building workshop conducted by June 2023 | 2 capacity building workshop conducted by June 2024 | 1 capacity building workshop conducted | N/A | Target Achieved. 01 Capacity Workshp conducted | N/A | N/A | 1 capacity building workshop conducted | N/A | R 20 000 | Report and attendance registers | Community services
GGPP 29 | Elderly and disability programmes | Coordination of events | To provide support to disability and elderly groups | BLM | Number events coordinated by June 2024 | Two programmes supported | 02 events coordinated by June 2024 | 1 event coordinated | N/A | Target Achieved. 01 Eldery and disability event coordinated on the | N/A | N/A | 1 event coordinated | N/A | R 120 000 | Report and attendance registers | Community services
GGPP 30 | Elderly and disability programmes(Council meetings) | meetings | To provide support to disability and elderly groups | BLM | Number elderly and disability council meetings coordinated by June 2024 | 4 elderly and 4 disability council meetings coordinated by June 2023 | 4 elderly and 4 disability council meetings coordinated by June 2024 | 1 elderly and 1 disability council meetings coordinated | 1 elderly and 1 disability council meetings coordinated | Target Achieved. 02 Elderlly and 02 disabllity council meetings cordinated on the 25th and 31st October 2023 | N/A | N/A | 1 elderly and 1 disability council meetings coordinated | 1 elderly and 1 disability council meetings coordinated | R 60 000 | Reports | Community services
GGPP 31 | Elderly and disability programmes(Capacity building) | Workshops | To provide support to disability and elderly groups | BLM | Number capacity building workshop conducted by June 2024 | 02 capacity building workshop conducted by June 2023 | 02 capacity building workshop conducted by June 2024 | 1 capacity building workshop conducted | N/A | Target Achieved. 01 Capacity Building workshop conducted | N/A | N/A | 1 capacity building workshop conducted | N/A | R 80 000 | Reports | Community services
GGPP 32 | Youth and children programme(Youth Council meetings) | meetings | To provide support to Youth and children | BLM | Number Youth Council meetings held by June 2024 | 4 Youth Council meetings held by June 2023 | 4 Youth Council meetings held by June 2024 | 1 Youth Council meetings held | 1 Youth Council meetings held | Target Achieved. 02 Youth Council meetings were held | N/A | N/A | 1 Youth Council meetings held | 1 Youth Council meetings held | R 80 000 | Reports | Community services
GGPP 33 | Youth and children programme(Back to school campaign) | Conduct the back to school campaign | To provide support to Youth and children | BLM | Number schools visited during back to campaign by June 2024 | Two back to school campaigns conducted. | 10 schools visited during back to campaign by June 2024 | N/A | N/A | N/A | N/A | N/A | 10 schools visited during back to campaign | N/A | R 50 000.00 | Report and attendance registers | Community services
GGPP 34 | Youth and children programme(Career guidance and EXPO) | Coordination of event | To provide support to Youth and children | BLM | Number Career guidance and EXPO held by June 2024 | 1 Career guidance and EXPO held by June 2023 | 1 Career guidance and EXPO held by June 2024 | 1 Career guidance and EXPO held | N/A | N/A | N/A | N/A | N/A | N/A | R 27 000 | Reports | Community services
GGPP 35 | Youth and children programme(Commemoration of youth month) | Coordination of event | To provide support to Youth and children | BLM | Number Youth month commemoration event hosted by June 2024 | 1 Youth month commemoration event hosted by June 2023 | 1 Youth month commemoration event hosted by June 2024 | N/A | N/A | N/A | N/A | N/A | N/A | Number Youth month commemoration event hosted by June 2024 | R70 000 | Reports | Community services
GGPP 36 | Youth and children programme(Youth capacity building) | Workshops | To provide support to Youth and children | BLM | Number youth capacity building event conducted by June 2024 | Support to youth programs | 4 youth capacity building event conducted by June 2024 | 1 youth capacity building event conducted | 1 youth capacity building event conducted | Target Achieved. 02 Capacity Workshp conducted on the 14th October 2023 | N/A | N/A | 1 youth capacity building event conducted | 1 youth capacity building event conducted | R 70 000 | Report and attendance registers | Community services
GGPP 37 | Youth and children programme(Children' day) | Support to the children programs | To provide support to Youth and children | BLM | Number children’s day celebrated by June 2024 | Two children’s programs supported | 1 children’s day celebrated by June 2024 | 1 children’s day celebrated | N/A | N/A | N/A | N/A | N/A | N/A | R 100 000 | Report and attendance registers | Community services
GGPP 38 | Youth and children programme(Take a child to work) | Coordination of event | To provide support to Youth and children | BLM | Number take a child to work campaign conducted by June 2024 | Two children’s programs supported by June 2023 | 01 Take a child to work campaign conducted by June 2024 | 01 Take a child to work campaign conducted | N/A | N/A | N/A | N/A | N/A | N/A | R 100 000 | Reports | Community services
GGPP 39 | Mayor – Magoshi | Hosting of Mayor Magoshi | Improved stakeholder relations | BLM | Number Mayor-Magoshi meetings held by June 2024 | Four Mayor-Magoshi meetings held by June 2023 | Four Mayor-Magoshi meetings held by June 2024 | One Mayor-Magoshi meetings held | One Mayor-Magoshi meetings held | Target Achieved. Mayor agoshi meetings were held | N/A | N/A | One Mayor-Magoshi meetings held | One Mayor-Magoshi meetings held | R100 000.00 | Reports and registers | Community services
SPATIAL RATIONALE
NDP | ACTIVE ENGAGEMENT OF CITIZENS IN THEIR OWN DEVELOPMENT
OUTCOME 9 | ACTION SUPPORTIVE TO HUMAN SETTLEMENT(OUTPUT 1)
Project Details
Project/KPI Number | Project Name | Project Description (major activities) | Strategic Objective | Location | Key Performance Indicator | 2023-23 Baseline | 2023-24 Annual Target | Quarterly Projections | [6 empty] | 2023-24 Budget | Portfolio of evidence | Responsible Department
[8 empty] | Q1 | Q2 | Q2 Actual Performance | Reason for variance | Corrective Measure | Q3 | Q4
SPR 09 | Township development | Conduct township establishment process | To formalise rural and urban settlements | BLM | number of townships development conducted by June 2024 | 9 twoships developed | I townshp developed by June 2024 | Advertsiment, Briefing and appointment. | Phase 2 Inception report, conduct specialist studies( Geo-tec, EIA), Submission of draft layout plan | Target Not Achieved | delays in SCSM | Fastrack appointment of the service provider | Submission of applications to relevant departments for comments. | Proof of submision of approval of EIA | R1.1m | Reports | Economic Development and Planning
SPR 10 | Municipal Planning Tribunal | Coordination meetings | To determine land use and and developmentapllications | BLM | Number of planning tribunal meetings held by June 2024 | New indicastor | 2 Planning tribunal meetings held by June 2024 | Vetting, appointment and advertisement of appointed tribunal members | 1 sitting per quarter | Target not achieved | There were delays in the process due re-advertisement and vetting process | Tribunal has been appointed it awaiting gazetting processes. | N/A | 1 sitting per quarter | R250.000 | Reports | Economic Development and Planning
SPR 11 | Fire resistant cabinet files | Procurement through SCM processes | To safegaurd building plans files | BLM | Number Fire resistance cabinets purchased by June 2024 | New indicastor | 2 Fire resistance cabinets by June 2024 | Facilitate specification for procurement process | Facilitate appointment of service provider | Target Not Achieved. | Delays in the appoinmen of the service provider | Fast track appointment of the service provider | N/A | N/A | R 100 000 | Specification and delicery note | Economic Development and Planning

## SUMMARY OF UNACHIEVED TARGETS
SUMMARY OF UNACHIEVED TARGETS
No | TARGET | ACTUAL PERFORMANCE | REASON VARIANCE | CORRECTIVE MEASURE | DEPARTMENT
BSID 4 | 5 Transformers reconditioned. | Target not achieved | Delay in appointment of the service provider | Scm to fast-track the appointment of the service provider | Technical services
BSID 8 | 10 Poles purchased and installed | Target not Achieved. 10 Poles not purchased and installed | Delay in appointment of the service provider | Scm to fast-track the appointment of the service provider | Technical services
BSID 13 | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor. | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Technical services
BSID 14 | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor. | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Technical services
BSID 15(1) | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor done | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Technical services
BSID 15(2) | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor done | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Technical services
BSID 15(3) | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor done | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies alredy closed for builder holidays. | Technical services
BSID 15(4) | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor done | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Technical services
BSID 15(5) | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment. | Target not Achieved.Construction stage – Appointment of Contractor done | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Technical services
BSID 16 | Construction stage – Appointment of Contractor, Site Hand Over and Site Establishment, Construction Commencement | Target not Achieved.Construction stage – Appointment of Contractor done | Delay in appointment of the service provider | Site hand over and Site establishment will be done in the third quarter as construction companies already closed for builder holidays. | Technical services
BSID 18 | Patching of 50 sqm of potholes, construction of 1 speed hump, installation of 2 road signs, 1km of sweeping and 30 sqm of road markings | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | Technical services
BSID 19 | Patching of 50 sqm potholes and 50 sqm of road markings | Target Not Achieved. Specification submitted for appointment of service provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | Technical services
BSID 20 | Installation of 20 road signs, 50sqm of road markings and construction of 05 speed humps complete with markings. | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | Technical services
BSID 21 | 100sqm of road markings, installation of 05 road signs and 3.0 km of sweeping | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | Technical services
BSID 24 | 50 sqm of potholes patching, 50 sqm of road markings and sweeping of 1 kilometer of internal street | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | Technical services
BSID 25 | Installation of 04 road signs, 150 sqm of potholes patching, construction of 02 speed humps,50sqm of road markings | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | Technical services
BSID 26 | Installation of 12 road signs and construction of 06 speed humps, and 50 square meters of road markings | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the thrid quarter as manufacturing companies will be closing for builder holidays | Technical services
BSID 27 | 100sqm of road markings and 1km of sweeping | Target Not Achieved. Specification submitted for appointment of service provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | Technical services
BSID 28 | 50 square meters and 1,1km of road markings | Target Not Achieved. At BAC for appoitment of servcie provider | Delay in appointment of the service provider | Services to be rendered in the third quarter as manufacturing companies will be closing for builder holidays | Technical services
BSID 29 | Construction of 22 culverts and construction of 08 wingwalls | Target Not Achieved. 06 x 900mm pipe culverts installed at Avon | Installation of 22 culverts not achieved due to operational challenges (Diesel). Specification for costruction of wingwalls submitted to SCM for appoitnemnet of service provider | N/A | Technical services
MTOD 01 | 1 Tracker and 1 Chassis purchased | Target not Achieved. | Immediate need for 4 bakkies in electrical unit and three sedans for traffic unit | Proposal for adjustment of target. | Corporate services
MTOD 04 | Installation of devices. | Target not achieved. Devices were only installed in the main office | Installation delays on the part of service provider | Meeting to be held with service provider by end of January 2024 | Corporate services
MTOD 09 | 15 councillors to be trained. | Target not Achieved Appoitment of Service providers ntot done and Only councilors were trained | Government institurions will reopen in the 03rd quarter | Revision of the target to be completed in the 03rd quarter | Corporate services
MTOD 10 | 20 Employees trained | Target not achieved. Serrvice providers not appointed and Only 3 employees are currently enrolled for CPMD with the university of Witwatersrand | Most identified isntitutins can only accommodate potential trainees from the 03rd quarter | Revision of the target be completed in the 03rd quarter | Corporate services
MTOD 16 | 90 employees provided with protective clothing. | Target not achieved. The service provider was appointed on a two year contract but protective clothing for the current financial year is yet to be delivered | Delay in delivery on the part of the service provider | Protective clothing to be delivered during the third quarter | Corporate services
BSID 49 | Upgrading of Tolwe satelite | Not achieved | Specification for the remaining scope of work was developed and submitted to Finance for further processes. Waiting for the advert. | The project is then shelved for the next quarter. | Corporate services
MTOD 20 | Procurement of Household Wheelie Bins. | Not achieved | Specifications Submitted to the SCM, Still waiting for response. | Still waiting for Finance Processes | Community services
MTOD 23 | Sign Boards, Notice and Flyers. | Not achieved | Specifications submitted to SCM .Still Waiting for response. | Still Waiting for Finance Processes. | Community services
MTOD 30 | 100 Trees Purchased | Not achieved | Still Waiting for SCM Processes. | Fast track purchase of trees with SCM. | Community services
MTOD 31 | Procurement of Cemetery Record Books | Not achieved | Still Waiting for SCM Processes | Fast Track Purchase of SCM | Community services
MTOD 37 | 100% Percentage Traffic Stationery Purchased . | Not achieved | Specifications Submitted to SCM .Still Waiting for Response. | Still Waiting for Finance Processes. | Community services
MTOD 42 | 10 Sets of Uniform Purchased for Law Enforcement Personnel . | Not achieved | Specifications Submitted to SCM. Still Waiting for Response. | Fast Track Purchase of PPE with SCM, | Community services
MTOD 46 | Maintenance of Sports Facilities. | Not achieved | Specification and Procurement Not Achieved. | Specification Submitted to SCM. | Community services
MTOD 47 | Maintenance of Community Halls | Not achieved | Specification and Procurement Not Achieved. | Specifications Submitted to SCM. | Community services
MTOD 48 | Purchase of Disaster Relief Material. | Not achieved | Specification Submitted to SCM. | To Fast the SCM Processes | Community services
MFVM 17 | 1 x revenue management meeting to be held | Target not Achieved. | The meeting was scheduled for November/December but the audit was during its peak and the committee could not seat. | The meeting will take place in the 3rd quarter. | Budget and treasury
LED 01(1) | LED Projects | SMME’s projects to be supported this financial year identified | Delay in procurement processes | Supply chain to fastrack procurement process | Economic Development and Planning
SPR 09 | Township Establishment | Inception report, conduct specialists studies(Geotech and EIA) and submission of draft layout plan | Delay in SCM processes | The SCM office to fast-track the processes | Economic Development and Planning
SPR 10 | Municipal Planning Tribunal | 1 Sitting per quarter | Delay in appointment,Vetting and gazetting | To fastrack issue of gazzetting | Economic Development and Planning
SPR 11 | Fire Resistant cabinet Files | Appointment of service provider | Delay in procurement process | Supply chain to fast-track the appoint of service provider | Economic Development and Planning
GGPP 01 | One unqualified audit opinion obtained for 2022-23 financial year | Target Not Achieved. Received qualified opinion | Issues related to Assets raised in AG's Management report | To address raised issues in the Audit Action Plan | MM' Office
MTOD 54 | 100% installation new camera system by June 2024 | Target Not Achieved | Delays in SCM processes | To fast track the SCM processes | MM' Office
MTOD 55 | 100% installation access control system by June 2024 | Target Not Achieved | Delays in SCM processes | To fast track the SCM processes | MM' Office