## Cover
APPROVED BLM Q4 SDBIP 2023-24 REPORT
VISION
A participatory municipality that turns prevailing challenges into opportunities for growth and development through optimal utilization of available resources
MISSION
To ensure delivery of quality services through community participation and creation of an enabling environment for economic growth and job creation

## Q4 SUMMARY PER DEPT
Department | Total Fourth Quarter Targets | Targets Achieved | Targets not achieved | Achievement in Percentage
Corporate Services | 7 | 7 | 0 | 100%
Community Services | 22 | 22 | 0 | 100%
Economic Development & Planning | 6 | 6 | 0 | 100%
Budget & Treasury | 11 | 11 | 0 | 100%
Technical Services | 21 | 14 | 7 | 67%
Municipal Managers 'Office | 3 | 3 | 0 | 100%
Overall Total Targets | 70 | 63 | 7 | 90%
7
APPROVED BY
RAMOTHWALA RJ
MUNICIPAL MANAGER

## SDBIP per KPA (2)
APPROVED BLM Q4 SDBIP 2023-24 REPORT
KPA | BASIC SERVICES AND INFRASTRUCTURE DEVELOPMENT
NDP | BUILDING KEY CAPABILITIES(HUMAN,PHYSICAL AND INSTITUTIONAL
OUTCOME 9 | IMPROVE ACCESS TO BASIC SERVICES ( OUTPUT 2)
Project Details
Project/KPI Number | Project Name | Project Description (major activities) | Strategic Objective | Location | Key Performance Indicator | 2022-23 Baseline | 2023-24 Annual Target | Q4 Targets |  |  |  | 2023-24 Budget | Portfolio of evidence | Responsible Department
[9 empty] | Actual Performance | Reason for Variance | Corrective Measures
BSID 1 | Electrical Equipment | Purchasing of identified Electrical equipment | To ensure minimal energy consuption by users as per the national energy reduction strategy | BLM | Number identified sets of electrical equipment purchased by June 2024 | 25 Electrical equipment purchased by June 2023 | 30 Identified sets of Electrical equipment purchased by June 2024 | 10 Identified sets of Electrical equipment purchased . | Target Not Achieved. 08 Identified sets of Electrical equipment purchased. | Budget constraints | Allocate enough budget for the purchase of the identified set of electrical equipment. | 1908000 | Proof of Purchase and list of electrical equipment purchased | Technical services
BSID 3 | Transformers | Purchasing and Installation of emergency Transformers | To ensure uninterrupted energy supply to communities | BLM | Percentage ermegency transformers purchased and installed as an when required by June 2024 | 100% ermegency transformers purchased and installed as an when required. | 100 % Purchasing and Installation of emergency Transformers as an when required by June 2024 | 100 % Purchasing and Installation of emergency Transformers as an when required | Target Achieved. 100 % Purchasing and Installation of emergency Transformers as an when required | N/A | N/A | 587000 | Proof of Purchase and Transformer register | Technical services
BSID 7 | Electricity token Identify(TID) ROLL OVER | Upgrading and replacement of meters installed before 2015 to STS6 compliant by November 2024 | To ensure uninterrupted energy supply to communities | BLM | Number meters upgraded and number meters replaced by June 2024 | New indicator | 6 380 meters upgraded and 2000 replaced meters by June 2024 | 3880 meters upgraded and 1000 replaced meters by June 2024 | Target achieved. 3880 meters upgraded and 1000 replaced meters by June 2024 | N/A | N/A | R 2 993 000 | Replacement and upgrading of meters reports | Budget & Treasury
BSID 8 | Electrical Poles | Purchasing and replacement of poles | To ensure uninterrupted energy supply tocommunities | BLM | Number Poles purchased and installed by June 2024 | 30 Poles purchased and installed at Grootpan, The-Grange and Simpson by June 2023 | 20 Poles purchased and installed by June 2024 | N/A | N/A | N/A | N/A | R 200 000.00 | Proof of Purchase and pictures,List of areas were poles were installed | Technical services
BSID 13 | Electrification of extensions | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Alldays village | Number households electrified and energized at Alldays village by June 2024 | New indicator | 60 households electrified and energised at Alldays village by June 2024 | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 60 connections at Alldays | Target Achieved. Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 60 connections at Alldays | N/A | N/A | 1,360,329,00 | Advert, appointment letters, site hand over minutes, pictures and Completion certificate | Technical services
BSID 14 | Electrification of extensions | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Mochemi village | Number households electrified and energized at Mochemi village by June 2024 | New Indicator | 25 households electrified and energised at Mochemi village by June 2024 | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 25 connections at Mochemi | Target Achieved. Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 25 connections at Mochemi | N/A | N/A | R 350 000 | Advert, appointment letters, site hand over minutes, pictures and Completion certificate | Technical services
BSID 15(1) | Electrification of extensions | onfirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Bayswater village | Number households electrified and energized at Bayswater village by June 2024 | New indicator | 30 households electrified and energised at Bayswater village by June 2024 | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 30 connections at Bayswater | Target Achieved. Testing and commissioning of 30 connections at Bayswater completed. | N/A | N/A | 536 079 | Advert, appointment letters, site hand over minutes, pictures and Completion certificate | Technical services
BSID 15(2) | Electrification of extensions | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Mongalo village | Number households electrified and energized at Mongalo village by June 2024 | New indicator | 50 households electrified and energised at Mongalo village by June 2024 | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 50 connections at Mongalo | Target Achieved. Testing and commissioning of 50 connections at Mongalo completed. | N/A | N/A | 1000000 | Advert, appointment letters, site hand over minutes, pictures and Completion certificate | Technical services
BSID 15(3) | Electrification of extensions | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Simpson village | Number households electrified and energized at Simpson village by June 2024 | New indicator | 25 households electrified and energised at Simpson village by June 2024 | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 25 connections at Simpson | Target Achieved. Testing and commissioning of 25 connections at Simpson completed | N/A | N/A | 217 968 | Advert, appointment letters, site hand over minutes, pictures and Completion certificate | Technical services
BSID 15(4) | Electrification of extensions | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Swartz village | Number households electrified and energized at Swartz village by June 2024 | New indicator | 45 households electrified and energised at Swartz village by June 2024 | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 45 connections at Swartz | Target Achived. Testing and commissioning of 45 connections at Swartz completed. | N/A | N/A | 900000 | Advert, appointment letters, site hand over minutes, Quarterly Progress reports, pictures and Completion certificate | Technical services
BSID 15(5) | Electrification of extensions | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To connect and provide sustainable energy to all households by June 2024 | Sweethome village | Number households electrified and energized at Sweethome village by June 2024 | New indicator | 70 households electrified and energised at Sweethome village by June 2024 | Construction stage - Transformer mounting and house connections COMPLETION STAGE: Testing and commissioning of 70 connections at Sweethome | Target Achieved. Testing and commissioning of 70 connections at Sweethome completed. | N/A | N/A | 1400000 | Advert, appointment letters, site hand over minutes, Quarterly Progress reports, pictures and Completion certificate | Technical services
BSID 16 | Construction of Senwabarwana Substation Phase 3 | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To provide sustainable energy to all households | Senwabarwana electricity substation Phase 3 | Number 20MVA 132/22KV Power Transformer, NECRT, AC/DC Distribution panel procured and installed and contruction 100 metres paving Internal Access Road by June 2024 | Perimeter fence(120m), Drilling and equipping of borehole(01) and Building of Substation House(160m2) ,Paving (350m2),Access road (1.3km). Construction of Primary Plant Platform, Construction of Primary Plant Equipment Foundations, Supply and Installation of Primary Plant Equipments by June 2023 | Procurement and installation of 1 x 20MVA 132/22KV Power Transformer, 1X NECRT, 1 x AC/DC Distribution panel and contruction 100 metres paving Internal Access Road by June 2024 | Construction of Access Road and Installation of Power Transformer, NECR and 22KV Switchgear | Target Not Achieved. Construction of Access Road and Installation of Power Transformer, NECR and 22KV Switchgear not done as we still waiting for the delivery of the long lead materials( Transformers and Switchgear Panels) | Manufacturing processes of the materials takes long. | Constant follow-up with the suppliers, to fastrack the delivery of the long lead materials. | 27800000 | Advert, appointment letters, site hand over minutes, Project Progress reports, pictures | Technical services
BSID 17 | Roads (Maintenance) | Maintenance of roads | To maintain internal streets and access roads on continuous basis | Senwabarwana | Number set of identified road maintenance materials purchased by June 2024 | 700 Square meters of patching potholes and 50 square meters of road markings at Senwabarwana Internal Streets by June 2023 | 10 x 210L emulsion drums, 700 x 25 kg cold mix bags and 10 x 20L road marking paints purchased for Senwabarwana Internal Streets by June 2024 | Procurement of 05 x 210L emulsion drums, 10 x 20L road marking paints and 500 x 25kg cold mix bags | Target Not Achieved specification and evaluation report done. | Delay in appointment of the service provider | Timeous appoinment of service providers for procurement of materials | 324000 | Proof of purchase | Technical services
BSID 29 | Culverts | Construction of new culverts and wingwalls | To construct low water bridges | BLM | Number of culverts constructed complete with wing-walls and number culverts purchased by June 2024 | 64 new culverts and 14 wingwalls constructed by June 2023 | 06 Culverts and 4 wingwalls constructed and 60 culverts purchased by June 2024 | Construction of 04 wingwalls | Target Not Achieved. Specification submitted for appoinment of service provider for contruction of wingwalls | Delay in appointment of the service provider | Timeous appoinment of service providers for procurement of materials | R 286 000.00 | Proof of Purchase,Photographs, Ward Councillors confirmation letter | Technical services
BSID 32 | Road Maintenance Materials | Purchase of identified sets road materials | Improve maintenance capacity | BLM | Number set of identified road maintenance materials purchased by June 2024 | 4 sets of identified road maintenance materials purchased by June 2023(Wheel barrows(05),Brooms(30),square shovels(10) and digging spades(10) by June 2023 | 4 sets of identified road maintenance materials purchased by June 2024(Wheel barrows(05),Brooms(30),square shovels(10) and digging spades(10). | N/A | N/A | N/A | N/A | R20,000,00 | Proof of purchase and list of sets of materials purchased | Technical services
BSID 37 | Construction of Danzig Creche | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To provide safe and sustainable educational facility services | Danzig | Percentage construction of Danzig Creche Completed by September 2023 | Appointment of contractor, Site handover,Site setablishment,Foundations, Drilling of borehole, Brickwork Super structure upto wall plate level completed by June 2023 | 100% construction of Danzig Creche Completed by September 2023 (100% construction of Superstructure with roofing,fencing,Kids play ground. Drilling of borehole and septic tank | N/A | N/A | N/A | N/A | R1,051,332 | Advert,appointment letters,handover minutes,Site visit report ,pictures and Completion certicate | Technical services
BSID 38 | Construction of Mongalo Creche | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To provide safe and sustainable educational facility services | Mongalo | Percentage construction of Mongalo Creche Completed by September 2023 | Appointment of contractor, Site handover,Site setablishment,Foundations, Drilling of borehole, Brickwork Super structure upto wall plate level completed by June 2023 | 100% construction of Mongalo Creche Completed by September 2023 (100% construction of Superstructure with roofing,fencing,Kids play ground. Drilling of borehole and septic tank) | N/A | N/A | N/A | N/A | 992.289 | Advert,appointment letters,handover minutes,Site visit report ,pictures and Completion certicate | Technical services
BSID 40 | Construction of Mochemi access and internal streets | Confirmation of the Project on the IDP, Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To ensure availabity of infrastructure to support public transport | Mochemi | Kilometres of Roadbed layer, Sub base, base layer and interlocking pavement for Mochemi access road and internal street completed by June 2024 | New Indicator | Construction of 4.4 Km of Roadbed layer, Sub base, base layer and interlocking pavement for Mochemi access road and internal street completed by June 2024 | 4,4 km construction of Sub-base, base layerworks and interlocking pavement for Mochemi access road and internal street completed bu June 2024 | Target not Achieved.4,4 km construction of Sub-base, base layerworks and interlocking pavement for Mochemi access road and internal street | Delay in delivery of materials from the supplier | constant follow-up with the suppliers, to fastrack the delivery of the materials. | R 35 200,000.00 | Advert,appointment letters,handover minutes,Site visit report ,pictures and progress report. | Technical services
BSID 41 | Construction of Lethaleng to Pickum access road | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To ensure availabity of infrastructure to support public transport | Lethaleng and Pickum | Kilometres of Roadbed layer and Sub base and base layer for Lethaleng to Pickum access road completed by June 2024 | New Indicator | Construction of 6,2 km of Roadbed layer and Sub base and base layer for Lethaleng to Pickum access road completed by June 2024 | 6,2 km construction of Sub-base and base layerworks for Lethaleng to Pickum access road completed by June 2024 | Target Achieved. 6,2 km construction of Sub-base and base layerworks for Lethaleng to Pickum access road completed by June 2024 | N/A | N/A | R 24,773,378.72 | Advert,appointment letters,handover minutes,Site visit report ,pictures | Technical services
BSID 49 | Upgrading of Tolwe Satellite office | Appointment of service provider and construction | To improve office space | Tolwe Satelite office | Percentage upgrading of Tolwe satellite office completed by June 2024 | New indicator | 100% upgrading of Tolwe satellite office completed by June 2024(Construct admin block entrance(01),cashier pay point 900X1,8m),floor tiles(classes and service point center),air conditioners(2),wall plugs(5),wooden doors(5),electrical work(Whole structure) | N/A | Target Achieved Tolwe Building Completed | N/A | N/A | R200 000.00 | Progress Report | Community Services
BSID 52 | Indigent relief | Provision of indigent services | To provide indigent relief | BLM | Number Indigent households provided with free basic electricity by June 2024 | New Indicator | 3500 Indigent households provided with Free basic electricity by June 2024 | 3500 Indigent households provided with Free basic electricity | Target achieved. 3500 Indigent households provided with Free basic electricity | N/A | N/A | OPEX | Indigents register | Budget & Treasury
BSID 53 | Re-graveling of Ga-Kgatla Access Road and stormwater control (4.0km) | Confirmation of the Project on the IDP, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To ensure availabity of infrastructure to support public transport | Ga-Kgatla | Number Design report developed and approved,site handover ,establishment,clearance and setting out completed for Ga-Kgatla access road and stormwater control by June 2024 | New Indicator | 01 Design report developed and approved,site handover ,establishment,clearance and setting out completed for Ga-Kgatla access road and stormwater control by June 2024 | Planning stage Inception and Preliminary Design development, Design approval, Site handover and site establishment. Site clearance and setting out. | Target Achieved. Planning stage Inception and Preliminary Design development, Design approval, Site handover and site establishment. Site clearance and setting out. | N/A | N/A | R 5,100,000,00 | Advert,appointment letter,Site handover minutes and project progress report | Technical services
BSID 54 | Rehabilitation of Senwabarwana Internal Streets and Stormwater Control | Confirmation of the Project on the IDP, Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To ensure availabity of infrastructure to support public transport | Senwabarwana | Number Design report developed and approved for Senwabarwana internal street and stormwater control completed by June 2024 | New Indicator | 01 Design report developed and approved for Senwabarwana internal street and stormwater control completed by June 2024 | Design approval | Target Achieved. Design report appoved | N/A | N/A | R 25,000,000,00 | Planning stage inception and preliminary development and detailed approved design report | Technical services
BSID 55 | Rehabilitation of Alldays Internal Streets and Stormwater Control | Confirmation of the Project on the IDP, Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To ensure availabity of infrastructure to support public transport | Alldays | Number Design report developed and approved for Alldays internal street and stormwater control completed by June 2024 | New Indicator | 01 Design report developed and approved for Alldays internal street and stormwater control completed by June 2024 | Design approval | Target Achieved. Design report appoved | N/A | N/A | R 17,000,000,00 | Planning stage inception and preliminary development and detailed approved design report | Technical services
BSID 56 | Construction of electricity substation at Senwabarwana | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To provide sustainable energy to all households | Senwabarwana electricity substation phase 2 | Number Substation constructed at Senwabarwana(Phase 2) by June 2024 (Isolators(132kv)Current transformers(132kv),Voltage transformers(132kv)Circuit breakers(132kv),Twin tubular bus bars bar(132kv),Columns(132kv), highmast lights and Perimeter fence(2,4m hightx170m length) by June 2024 | Perimeter fence(120m), Drilling and equipping of borehole(01) and Building of Substation House(160m2) ,Paving (350m2),Access road (1.3km) | 01 substation constructed at Senwabarwana(Phase 2) by June 2024 (Isolators(8x132kv)Current transformers(15x132kv),Voltage transformers(6x132kv)Circuit breakers(5x132kv),Twin tubular bus bars bar(2x132kv),Columns(2x132kv),4 x highmast lights and Perimeter fence(2,4m hightx170m length) by June 2024 | COMPLETION STAGE - Mounting Equipment on the Steel support structures, Stringing of Conductors and Yard Stoning. | Target not Achieved Mounting Equipment on the Steel support structures, Stringing of Conductors and installation of highmast light | Contractor encoutered hard rork on site on | The Contractor was informed to submit the revised catch-up plan in order to ensure that the project is completed by the end of September 2024. | R 5 412 286 | Advert, appointment letters, site hand over minutes, Project Progress reports, pictures and Completion Certificate. | Technical services
BSID 57 | Construction of Alldays Internal Street and Stormwater Control Phase 2 | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To ensure availability of infrastructure to support public transport | Alldays | Kilometres constructed at Alldays Internal Street from gravel to tar and Storm-water channel completed by June 2024 | New Indicator | Construction of 4.0 Km of Alldays internal street and stormwater control completed by June 2024 | N/A | N/A | N/A | N/A | R 1 310 249 | Advert,appointment letters,handover minutes,Site visit report ,pictures and Completion certicate | Technical services
BSID 58 | Construction of Avon Multipurpose community centre | Confirmation of the Project on the IDP, Project Registration, Compilation of Specification/ Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To provide safe and sustainable recreational and social facilities | Avon | Number multi-purpose Community centre constructed at Avon by June 2024 | New Indicator | Construction of one Mutli-purpose Community centre at Avon Completed by June 2024 | Completion stage:Avon Community centre Completed | Target Not Achieved Qoutation for the remaining scope of work submtted and awaiting aaproval | Contractor terminated | Consultant will be appointed as a turnkey to complete the remaining work | R974,902,00 | Advert,appointment letters,handover minutes,Site visit report ,pictures and Completion certicate | Technical services
BSID 59 | Re-graveling of Sefihlampšyana Access Road and stormwater control (6.0km) | Confirmation of the Project on the IDP, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To ensure availabity of infrastructure to support public transport | Sefihlampšyana | Kilometer re-gravelling of Sefihlampšyana internal street and stormwater control completed by June 2024 | New Indicator | 6km re-gravelling of Sefihlampšyana internal street and stormwater control completed by June 2024 | N/A | N/A | N/A | N/A | 4000000 | Advert,appointment letters,handover minutes,Site visit report ,pictures and Completion certicate | Technical services
BSID 60 | Construction of Thalane to Bosehla access road and stormwater control | Confirmation of the Project on the IDP, Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To ensure availabity of infrastructure to support public transport | Thalane to Bosehla | Number Design report developed and approved for Thalane to Bosehla access road and stormwater control by June 2024 | New Indicator | One Design report developed and approved for Thalane to Bosehla access road and stormwater control by June 2024 | One Design report developed and approved for Thalane to Bosehla access road and stormwater control | Target Achieved. One Design report developed and approved for Thalane to Bosehla access road and stormwater control | N/A | N/A | R2 196 524.00 | Scoping report ,preliminary design report and detailed approved design report | Technical services
BSID 61 | Construction of Kwarung internal street and stormwater control | Confirmation of the Project on the IDP, Registration, Compilation of Specification/Tender documents, Tender advert, Evaluation, Appointments, Design, Construction, closeout. | To ensure availabity of infrastructure to support public transport | Kwarung internal street and stormwater control | Number Design report developed and approved for Kwarung internal street and stormwater control by June 2024 | New Indicator | One Design report developed and approved for Kwarung internal street and stormwater control by June 2024 | One Design report developed and approved for Kwarung internal street and stormwater control | Target Achieved. One Design report developed and approved for Kwarung internal street and stormwater control | N/A | N/A | R1 965 220.00 | Scoping report ,preliminary design report and detailed approved design report | Technical services
KPA | INSTITUTIONAL TRANSFORMATION AND ORGANISATIONAL DEVELOPMENT
NDP | BUILDING CAPABLE AND DEVELOPMENTAL STATE
OUTCOME 9 |  | ADMINISTRATIVE AND FINANCIAL CAPABILITY
Project Details
Project/KPI Number | Project Name | Project Description (major activities) | Strategic Objective | Location | Key Performance Indicator | 2022-23 Baseline | 2023-24 Annual Target |  |  |  |  | 2023-24 Budget | Portfolio of evidence | Responsible Department
[8 empty] | Q4 | Actual performance | Reason for variance | Corrective measure
MTOD 09 | Training for councillors | conduct councilors training | To improve skills and maximize productivity | BLM | Number councillors trained by June 2024 | Councillors training report compiled by June 2023 | 22 Councillors trained by June 2024 | N/A | N/A | N/A | N/A | R 500 000.00 | Councillors training report | Corporate services
MTOD 10 | Training for officials & Interns | conduct employees training | to improve skills and maximize productivity | BLM | Number of employees trained by June 2024 | 31 Employees trained by June 2023 | 31 Employees trained by June 2024 | N/A | N/A | N/A | N/A | R 400 000 | Employees training report | Corporate services
MTOD 11 | Municipal employees bursaries | Support to employees | To improve skills and maximize productivity | BLM | Numbers report on employees bursary compiled by June 2024 | 1 report on employees bursary compiled by June 2023 | 1 report on employees bursary compiled by June 2024 | N/A | N/A | N/A | N/A | R 300 000 | Employee bursary report | Corporate services
MTOD 15 | Employee wellness | Conducting employee wellness | improve employees health and well-being, optimize perfomance and productivity | BLM | Number reports on the employee wellness programme compiled by June 2024 | 2 Reports on employee wellness conducted by June 2023 | 2 Reports on employee wellness programme compiled by June 2024 | N/A | N/A | N/A | N/A | R 128 150.00 | Employee wellness programme reports and attendance registers | Corporate services
MTOD 16 | Uniform and protective clothing | Purchasing of Uniform and protective clothing | To protect employees from exposure to work place hazards and the risk of injuries | BLM | Number of employees provided with protective clothing by June 2024 | 90 employees provided with PPE by June 2023 | 90 employees provided with protective clothing by June 2024 | 90 employees provided with protective clothing. | Target achieved. 90 employees provided with protective clothing. | N/A | N/A | R 700 000 | Delivery note and distribution register | Corporate services
MTOD18 | Conduct waste disposal facilities external audits | Conduct external Audits | To ensure efficient Waste Management | BLM | Number waste disposal facilities external audits conducted by June 2024 | New Indicator | 01 waste disposal facilities external audit conducted by June 2024 | N/A | N/A | N/A | N/A | R 200 000 | Waste facilities external audit report | Community Services
MTOD 20 | Procurement of household wheelie bins | Procurement | To ensure efficient Waste Management | BLM | 300 wheelie bins procured by June 2024 | New Indicator | 300 wheelie bins procured by June 2024 | N/A | N/A | N/A | N/A | R 390 000 | Proof of purchase | Community Services
MTOD22 | Conduct Cleaning Campaigns | Facilitation of Cleaning Awareness and Campains | To ensure awareness on waste management | BLM | Number of cleaning campaigns conducted by June 2024 | 04 cleaning campaigns conducted by June 2023 | 04 cleaning campaigns conducted by June 2024 | 01 cleaning campaigns conducted | Target Achieved cleaning campaign conducted on May 2024 at Senwabarwana . | N/A | N/A | OPEX | Cleaning campaigns reports and photos | Community Services
MTOD24 | Landfill maintenance | Maintenance of landfill sites | To ensure proper maintenance and operation of site | BLM | Number landfill site maintenance reports compiled by June 2024 | 12 landfill site maintenance reports compiled by June 2023 | 12 landfill site maintenance reports compiled by June 2024 | 3 landfill site maintenance reports compiled | Target Achieved. 03 Landfill site maintenance report compiled | N/A | N/A | R 4 900 000.00 | Landfill maintenance reports | Community Services
MTOD 30 | Climate Change mitigation | Purchase | Promote environmental management | BLM | Number Trees purchased by June 2024 | New Indicator | 100 Trees purchased by June 2024 | N/A | N/A | N/A | N/A | R 100 000 | Report | Community Services
MTOD31 | Procurement of cemetery record books | Procurement | To ensure that grave sites are registered | BLM | Number Cemetery record books purchased by June 2024 | 05 cemetery records books procured by June 2023 | 05 Cemetery record books procured by June 2024 | N/A | N/A | N/A | N/A | R 50 000.00 | Proof of purchase | Community Services
MTOD 36 | Calibration of speed machines | Calibration and reporting | Maintenance | BLM | Number Maintenance Report compiled by June 2024 | 4 Maintenance Report compiled by June 2023 | 4 Maintenance Report compiled by June 2024 | 1 Maintenance Report compiled | Target Achieved. 01 Maintenance report compiled | N\A | N/A | R 84 500.00 | Maintenance Report | Community Services
MTOD 37 | Procurement of stationery | Purchase | To ensure enough material for Traffic services | BLM | Percentage traffic stationery purchased by June 2024 | 100% Percentage traffic stationery purchased by June 2023 | 100% Percentage traffic stationery purchased by June 2024 | N/A | N/A | N/A | N/A | R 50 000.00 | Proof of purchase | Community Services
MTOD 38 | Catering for four awareness's | Coordinate awareness campaigns | To celebrate transport month and promote awareness | BLM | Number transport Awareness Events conducted by June 2024 | 2 transport Awareness Event conducted by June 2023 | 4 transport Awareness Events conducted by June 2024 | 1 transport Awareness Event conducted | Target Achieved Transport awareness campaign conducted on 14 june 2024 at Boslaagte. | N\A | N\A | OPEX | Transport awaeness events reports | Community Services
MTOD 39 | Maintenance of equipment | Maintenance | To ensure proper working equipment | BLM | Number VTS machines calibrated by June 2024 | 1 VTS machines calibrated by June 2023 | 1 VTS machines calibrated by June 2024 | N/A | N/A | N/A | N/A | R 84 500.00 | Equipment maintenance report | Community Services
MTOD 41 | Pound Awareness campaigns | campaigns | Promote safety | BLM | Number awareness campaigns conducted by June 2024 | 4 awareness campaigns conducted by June 2023 | 4 awareness campaigns conducted by June 2024 | 1 awareness campaigns conducted | Target Achieved Pound Awareness conducted on 25 April 2024 at Inveraan Multipurpose. | N/A | N/A | OPEX | Pound awareness campaigns reports | Community Services
MTOD 42 | Protective Clothing | purchase | Availability of PPE | BLM | Number set of uniform purchased for Law Enforcement Personnel by June 2024 | New Indicator | 10 sets of uniform purchased for Law Enforcement Personnel by June 2024 | N/A | N/A | N/A | N/A | R 200 000.00 | Proof of purchase | Community Services
MTOD45 | Maintenance of buildings | Maintenance | To ensure safe Municipal facilities | BLM | Number municipal buildings maintained by June 2024 | 3 municipal buildings maintained by June 2023 | 7 municipal buildings maintained by June 2024 | N/A | N/A | N/A | N/A | R 379 000 | Municipal building maintenance reports | Community Services
MTOD46 | Maintenance of Sports facilities | Maintenance | To ensure user-friendly Sports facilities | BLM | Number sports facilities maintained by June 2024 | 2 sports facilities maintained by June 2023 | 3 sports facilities maintained by June 2024 | N/A | N/A | N/A | N/A | R 1800 000 | Sports facilities maintenance reports | Community Services
MTOD47 | Maintenance of Community halls | Maintenance | To ensure user-friendly Community Halls | BLM | Number community halls maintained by June 2024 | 2 community halls maintained by June 2023 | 6 community halls maintained by June 2024 | N/A | N/A | N/A | N/A | R 130 000 | Community halls maintenance reports | Community Services
MTOD49 | Conduct Disaster Management education and awareness campaigns to communities | campaigns | To unsure effective Disaster Management | BLM | Number disaster education and awareness campaigns conducted by June 2024 | 4 Education and awareness campaigns conducted by June 2023 | 4 disaster Education and awareness campaigns conducted by June 2024 | 1 Disaster Education and awareness campaigns conducted | Target Achieved Disaster Awareness campaign conducted on 14 may 2024 at Ga-Kibi Moshate. | N\A | N\A | OPEX | Disaster Education and awareness campaigns reports | Community Services
MTOD 51 | IDP Steering Committees and Review Sessions | Compilation of quarterly SDBIP Reports | Compliance with legislations | BLM | Number of SDBIP Reports compiled by June 2024 | 4 SDBIP Reports compiled by June 2023 | 4 SDBIP Reports compiled by June 2024 | Third Quarter SDBIP Report 2023-24 | Target Achieved. Third Quarter SDBIP report compiled | N/A | N/A | R 530 000.00 | Quarterly SDBIP Reports | MM/Mayor’ Office
MTOD 52 | Performance Assessments | Conducting individual performance Assessments | Enhanced Municipal performance | BLM | Number individual performance assessments conducted(Annual and mid-year) by June 2024 | 2 Individual Assessments conducted(Annual and Mid-year) by June 2023 | 2 Individual Assessments conducted(Annual and Mid-year) by June 2024 | N/A | N/A | N/A | N/A | R30 000.00 | Individual Performance assessment Reports and Attendance Registers | MM/Mayor’ Office
MTOD 53 | Security Management | Appointment and payment of Physical Security service provider | Secure municipal property | BLM | Number Physical security services reports compiled by June 2024 | 12 Physical security services reports compiled by June 2023 | 12 Physical security services reports compiled by June 2024 | 3 Physical security services reports compiled | Target Achieved. 03 Physical services reports compiled | N/A | N/A | R 18 499 000 | Monthly Physical Security Reports | MM/Mayor’ Office
MTOD 56 | Gazetting of By-laws | Gazetting | Strengthen municipal legal services | BLM | Number by-laws gazetted by June 2024 | 3 by-laws gazetted by June 2023 | 5 by-laws gazetted by June 2024 | N/A | N/A | N/A | N/A | R 150 000 | Report on Gazetting of by-laws | Corporate services
MTOD 57 | Contract Management | Reports | Strengthen municipal legal services | BLM | Number contract management reports compiled by June 2024 | 4 contract management reports compiled by June 2023 | 4 contract management reports compiled by June 2024 | 1 contract management reports compiled | Target Achieved. 1 contract Management report compiled | N/A | N/A | OPEX | Contract Management Reports | Corporate services
MTOD 58 | Litigations | Compilation of reports | Strengthen municipal legal services | BLM | Number litigation reports compiled by June 2024 | 4 litigation reports compiled by June 2023 | 4 litigation reports compiled by June 2024 | 1 litigation report compiled | Target Achieved. Letigation report compiled | N/A | N/A | R 2 100 500 | Litigation Reports | Corporate services
KPA | LOCAL ECONOMIC DEVELOPMENT
OUTCOME 9 |  | IMPLEMENTATION OF COMMUNITY WORKS PROGRAMME
Project Details
Project/KPI Number | Project Name | Project Description (major activities) | Strategic Objective | Location | Key Performance Indicator | 2022/23 Baseline | 2023-24 Annual Target |  |  |  |  | 2023-24 Budget | Portfolio of evidence | Responsible Department
[8 empty] | Q4 | Actual performance | Reason for Variance | Corrective Measures
LED 01(1) | LED Projects | Financial support to identified LED Projects | To create and promote LED initiatives in the business sector | BLM | Number identified LED Projects Financially supported by June 2024 | 3 LED projects supported financially by June 2023 | 3 Identified LED Projects Financially supported by June 2024 | Project close out report | Target Achievd. 03 LED projects identified close out report compiled | N/A | N/A | R 650 000 | Reports and pictures | Economic Development & Planning
LED 1(2) | LED Summit | Coordination of a summit | To create and promote LED initiatives in the business sector | BLM | Number LED summit held by June 2024 | New Indicator | 1 LED summit held by June 2024 | N/A | N/A | N/A | N/A | R 170 000 | Reports and Attendance Register | Economic Development & Planning
LED 03 | Informal traders | management of hawkers | To create and promote LED initiatives in the business sector | BLM | Number quarterly reports on management of hawkers compiled by June 2024 | 4 quarterly reports on management of hawkers compiled by June 2023 | 4 quarterly reports on management of hawkers compiled by June 2024 | 1 quarterly report on management of hawkers compiled | Target Achieved. 01 Quarterly report on management of hawkers in ¦Senwabarwana and Alldays compiled | N/A | N/A | OPEX | Hawkers management reports | Economic Development & Planning
LED 05 | EPWP - Grant | Appointment of EPWP PRACTIONERS | To create job opportunities through EPWP programme | BLM | Number job opportunities created through EPWP programme by June 2024 | 235 opportunities created by June 2023 | 260 job opportunities created through EPWP programme by June 2024 | N/A | N/A | N/A | N/A | R 5 785 000 | List and EPWP reports | Community Services
KPA FINANCIAL VIABILITY AND MANAGEMENT
NDP | BUILDING OF KEY CAPABILITIES(HUMAN,PHYSICAL &INSTITUTIONAL)
OUTCOME 9 |  | ADMINISTRATIVE AND FINANCIAL CAPABILITY (OUTPUT 6)
Project Details
Project/KPI Number | Project Name | Project Description (major activities) | Strategic Objective | Location | Key Performance Indicator | 2022-23 Baseline | 2023-24 Annual Target |  |  |  |  | 2023-24 Budget | Portfolio of evidence | Responsible Department
[8 empty] | Q4 | Actual performance | Reason for Variance | Corrective Measures
MFVM 01 | Annual financial statement | Compilation of AFS | Enhance Sound Municipal financial viability and management | BLM | Number set of AFS Compiled & submitted to AGSA,LPT,COGOHSTA& NT by June 2024 | 2022-23 AFS compiled & submitted to AGSA, LPT& NT by June 2023 | 1 set of AFS Compiled & submitted to AGSA,LPT,COGHSTA & NT by June 2024 | N/A | N/A | N/A | N/A | R 1 150,000.00 | Acknowledgement of the receipt from AGSA | Budget & Treasury
MFVM 03 | Monthly budget statement(Sec 71 reports) | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | Number monthly budget statements submitted to Treasury within 10 working days after month-end | 12 monthly budget statements submitted to Treasury within 10 working days after month-end by June 2023 | 12 monthly budget statements submitted to Treasury within 10 working days after month-end by June 2024 | 3 monthly budget statements submitted to Treasury within 10 working days after month-end | Target Achieved. 03 Monthly budget statements submitted to Treasury within 10 working days after month end | N/A | N/A | OPEX | Monthly budget statement reports | Budget & Treasury
MFVM 05 | MSCOA projects implementation | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | Number MSCOA projects implementation reports compiled by June 2024 | 1 MSCOA projects implementation reports compiled by June 2023 | 4 x MSCOA projects implementation reports compiled by June 2024 | 1 x MSCOA projects implementation reports compiled | Target Achieved. 1X MSCOA projects implementation on reports compiled | N/A | N/A | OPEX | mSCOA Reports | Budget & Treasury
MFVM 06 | Reconciliations and registers | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | Number monthly reconciliation, registers and schedules compiled by June 2024 | 12 monthly reconciliation and registers reported to portfolio by June 2023 | 400 x monthly reconciliation, registers and schedules compiled by June 2024 | 100 x monthly reconciliation, registers and schedules compiled by June 2024 | Target Achieved. 100X Monthly reconcilliation, registers and schedules compiled | N/A | N/A | OPEX | Reconciliation, registers and schedules compiled/performed | Budget & Treasury
MFVM 07 | Annual Budget (Draft) | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | Number draft budget compiled and tabled by June 2024 | 1 draft budget compiled & tabled by June 2023 | 1 x draft budget compiled and tabled by March 2024 | N/A | N/A | N/A | N/A | OPEX | Draft Budget and Council Resolution | Budget & Treasury
MFVM 08 | Annual Budget (Final) | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | Number final budget compiled by June 2024 | 1 Final budget compiled by June 2023 | 1 x Final budget compiled by June 2024 | 1 x Final budget compiled | Target Achieved. 1X final budget compiled | N/A | N/A | OPEX | Final Budget and Council Resolution | Budget & Treasury
MFVM 09 | Adjustment budget | Compilation of adjustment budget | Enhance Sound Municipal financial viability and management | BLM | Number adjustment budget compiled by June 2024 | Adjustment budget compiled by June 2023 | 1 x adjustment budget compiled and submitted to council, LP & NT by June 2024 | N/A | N/A | N/A | N/A | OPEX | Budget adjustment and Council resolution | Budget & Treasury
MFVM 12 | Compile financial report, (section 52) | Compilation of report | Enhance Sound Municipal financial viability and management | BLM | Number quarterly financial reports compiled and reported to Executive Committee(EXCO) and Council by June 2024 | 4 x quarterly financial report compiled and reported to EXCO & Council by June 2023 | 4 x quarterly financial report compiled and reported to Executive committee and Council by June 2024 | 1 x quarterly financial report compiled and reported to EXCO & Council | Target achieved. 1 x quarterly financial report compiled and reported to EXCO & Council | N/A | N/A | OPEX | Quarterly financial reports | Budget & Treasury
MFVM 13 | Procurement plan | Compilation of report | Enhance Sound Municipal financial viability and management | BLM | Number procurement plan developed and approved by June 2024 | 1 x procurement plan developed and approved by June 2023 | 1 x procurement plan developed and approved by June 2024 | N/A | N/A | N/A | N/A | OPEX | Procurement plan | Budget & Treasury
MFVM 15 | Conduct training of SCM practitioner | Conduct training of SCM practitioner | Enhance Sound Municipal financial viability and management | BLM | Number SCM Training attended by June 2024 | 1 SCM Training attended by June 2023 | 1 x SCM Training conducted by June 2024 | 1 x SCM Training attended | Target Achieved, 01X SCM training attended | N/A | N/A | R 200,000.00 | SCM training report and Attendance Register | Budget & Treasury
MFVM 16 | Acquisition management(Bids Register) | Compilation of reports | Enhance Sound Municipal financial viability and management | BLM | Number updated awarded Bids reports by June 2024 | 12 x updated awarded Bids reports by June 2023 | 4 x updated awarded Bids placed on website by June 2024 | 1 x updated list awarded Bids placed on website | Target Achieved. 1x updated list awarded bids placed on the website | N/A | N/A | OPEX | List of awarded Bids (updated) | Budget & Treasury
MFVM 17 | Revenue management committee | Revenue management committee meetings to be held | Enhance Sound Municipal financial viability and management | BLM | Number revenue management meetings held by June 2024 | 2 revenue management meetings held by June 2023 | 4 x revenue management meetings to be held by June 2024 | 1 x revenue management meeting to be held | Target Achieved. 01x revenue management meeting held on the | N/A | N/A | OPEX | Minutes and Attendance Register | Budget & Treasury
MFVM 28 | Unbundling of Asset Register | Unbundling of Asset Register | Enhance Sound Municipal financial viability and management | BLM | Number unbundling of assets report compiled by June 2024 | 1 Asset unbundling reports compiled by June 2023 | 1 x unbundling of assets report compiled by June 2024 | N/A | N/A | N/A | N/A | R 1 100 000 | Unbundling of Asset report | Budget & Treasury
MFVM 30 | Reporting of incidents occurred | Reports | Enhance Sound Municipal financial viability and management | BLM | Number incidents reports compiled by June 2024 | 12 monthly incidents reports compiled by June 2023 | 12 monthly incidents reports compiled by June 2024 | 1 x incidents report compiled | Target Achieved 1X incidents report compiled | N/A | N/A | OPEX | Incidents Report | Budget & Treasury
KPA GOOD GOVERNANCE AND PUBLIC PARTICIPATION
NDP | ACTIVE ENGAGEMENT OF CITIZENS IN THEIR OWN DEVELOPMENT
OUTCOME 9 | DEEPEN DEMOCRACY THROUGH A REFINED WARD COMMITTEE MODEL(OUTPUT 5)
Project Details
Project/KPI Number | Project Name | Project Description (major activities) | Strategic Objective | Location | Key Performance Indicator | 2022-23 Baseline | 2023-24 Annual Target |  |  |  |  | 2023-24 Budget | Portfolio of evidence | Responsible Department
[8 empty] | Q4 | ActualPerformance
GGPP 01 | Auditing | Coordination of external Audit process | Improved audit opinion | BLM | Number unqualified audit opinion obtained for 2023-24 financial year by June 2024 | Unqualified audit opinion obtained for 2021-22 | 1 unqualified audit opinion obtained for 2023-24 financial year by June 2024 | N/A | N/A | N/A | N/A | R 5 000 000 | 2023-24 Audit report | MM/Mayor’ Office
GGPP 02 | Audit & Risk Committee Allowances | Coordination of Risk and Audit Committee meetings | Improved audit opinion | BLM | Number Risk and Audit Committee meetings by June 2024 | 08 meetings held by June 2023 | 04 Risk and 04 Audit Committee meetings by June 2024 | 01 Risk and 01 Audit Committee | Target Achieved. The meeting was held on the 26th April 2024 | N/A | N/A | R 400 000 | Minutes and Attendance Registers | MM/Mayor’ Office
GGPP 03 | Printing and Publication | Production of Municipal newsletter,diaries,calendars | To improve communication | BLM | Number newsletter editions,diaries and calendars produced by June 2024 | 2 editions newsletters, 100 diaries and 1000 calendars produced by June 2023 | 2 newsletter editions, 60 diaries and 2000 calendars produced by June 2024 | 1 newsletter edition produced | Target Achieved. The January - June 2024 was produced | N\A | N\A | R 200 000 | Copy of newletter, Reports and PoP | Corporate services
GGPP 04 | Publicity and Branding | procurement of banners and gazebos | Enhanced communication | BLM | Number banners and gazebos procured by June 2024 | 40 banners and 4 gazebos procured by June 2023 | 20 banners and 2 gazebos procured by June 2024 | N/A | N/A | N/A | N/A | R 350 000.00 | POP and delivery notes | Corporate services
GGPP 08 | Community Participation | Meetings | Enhanced Community participation | BLM | Number Council outreach programmes coordinated and supported by June 2024 | 6 Council outreach programmes coordinated and supported by June 2023 | 6 Council outreach programmes coordinated and supported by June 2024 | 2 Council outreach programmes coordinated and supported | Target Achieved. 2 Outreach programmes were coordinated and supported on the 30th of April 2024 and 03rd of May 2024 | N/A | N/A | R 1 000 000 | Council outreach report | Corporate services
GGPP 09 | Whippery Management | Meetings | Promote multiparty relations | BLM | Number Whippery management meeting coordinated and supported by June 2024 | 4 Whippery management meeting coordinated and supported by June 2023 | 4 Whippery management meeting coordinated and supported by June 2024 | 1 Whippery management meeting coordinated and supported |  | N/A | N/A | 200000 | Minutes and Attendance register | Corporate services
GGPP 10 | MPAC Programmes | Coordination of MPAC programmes | To improve public participation | BLM | Number MPAC programs coordinated by June 2024 | 5 programmes coordinated by June 2023 | 5 MPAC programs coordinated by June 2024 | N/A | N/A | N/A | N/A | R 790 000 | MPAC programmes report | Corporate services
GGPP 11 | Ward Committees’ Conference Programmes | Coordination and support | To improve public participation | BLM | Number Ward committee conference held by June 2024 | 01 Ward committee conference held by June 2023 | 01 Ward committee conference held by June 2024 | N/A | N/A | N/A | N/A | R1,853 000 | Ward Committee Conference Report | Corporate services
GGPP 12 | Remuneration of ward committees | Payment of stipends for Ward Committees | To improve public participation | BLM | Number Ward Committee members receiving monthly stipend by June 2024 | 220 Ward Committee members receiving monthly stipend by June 2023 | 220 Ward Committee members receiving monthly stipend by June 2024 | 220 Ward Committee members receiving monthly stipend | Target Achieved. 220 ward committee members received monthly stipends | N/A | N/A | R4,908 000.00 | Ward Committee meetings Report | Corporate services
GGPP 13 | Council support literature | Printing of Booklets | Pocket books to assist Councillors with Rules and Orders. | BLM | Number Rules of Order, Ward Committees’ Constitution and Service Delivery Charter booklets developed by June 2024 | Number of printed booklets by June 2023 | 60 Rules of Order, 250 Ward Committees’ Constitution and 100 Service Delivery Charter booklets developed by June 2024 | N/A | N/A | N/A | N/A | 200000 | Proof of purchase | Corporate services
GGPP 14 | IDP Review | Review of IDP/Budget | To ensure successful review of the IDP | BLM | Number IDP/Budget reviewed compiled by June 2024 | Number IDP/Budget reviewed compiled by June 2023. | 1 IDP/Budget reviewed compiled by June 2024 | 1 IDP/Budget reviewed compiled | Target Achieved, IDP\Budget reviewed and compiled | N/A | N/A | OPEX | Copy of IDP and Council resolution | Economic Development and Planning
GGPP 15 | IDP/Budget Process plan | development and approval of plan | To ensure successful review of the IDP | BLM | Number IDP Process plan developed and approved by June 2024 | 1 IDP Process plan developed and approved by June 2023 | 1 IDP Process plan developed and approved by June 2024 | N/A | N/A | N/A | N/A | OPEX | IDP Process plan and Council Resolution | Economic Development and Planning
GGPP 16 | IDP/Budget Booklets | Produce Booklets | To ensure successful review of the IDP | BLM | Number IDP Booklets produced by June 2024 | New indicator | 50 IDP Booklets produced by June 2024 | N/A | N/A | N/A | N/A | R 170 000 | Proof of purchase | Economic Development and Planning
GGPP 17 | Strategic planning sessions | Hold sessions | To ensure successful review of the IDP | BLM | Number strategic sessions held by June 2024 | 2 Strategic session held by June 2023 | 6 Strategic session held by June 2024 | 2 Strategic session held | Target achieved. 2 Strategic session held | N/A | N/A | R 650 000 | Strategic sessions Report and attendance registers | Economic Development and Planning
GGPP 18 | IDP/Budget Public participation | IDP stakeholder consultations | To ensure effective public participation in the review of the IDP | BLM | Number IDP consultative meetings conducted, IDP consultative reports compiled by June 2024 | 13 IDP consultative meetings conducted and One IDP consultative reports compiled by June 2023 | 13 IDP consultative meetings conducted and One IDP consultative reports compiled by June 2024 | 13 consultative meetings held | Target achieved. 13 consultative meetings held | N/A | N/A | R 636 000 | IDP Consultative reports and attendance registers | Economic Development and Planning
GGPP 19 | Development municipal multi sectoral implementation plan | development and approval of plan | To Provide support on HIV/AIDS progra | BLM | Number Municipal HAST plan approved by the Local AIDS council and submitted to DAC and LPAC by June 2024 | 1 plan developed and submitted by 2023 | 1 Municipal HAST plan approved by the Local AIDS council and submitted to DAC and LPAC by June 2024 | N/A | N/A | N/A | N/A | OPEX | Municipal Hast plan | Community services
GGPP 20 | Conduct HIV/AIDS programmes | meetings | Implementation HIV/AIDS programmes | BLM | Number M&E meetings held by June 2024 | 2 HIV/AIDS programmes coordinated by June 2023 | 4 M&E meetings held by June 2024 | 1 M&E meetings held | Target Achieved M&E Meeting held on 14 May 2024 at Alldays Clinic. | N\A | N/A | OPEX | Minutes and Attendance register | Community services
GGPP 21 | HIV/AIDS Council technical committee | meetings | Implementation HIV/AIDS programmes | BLM | Number AIDS Council technical committee meetings held by June 2024 | 2 HIV/AIDS programmes coordinated by June 2023 | 4 AIDS Council technical committee meetings held by June 2024 | 1 AIDS Council technical committee held | Target Achieved Local Council Technical meeting held on 10 June 2024 at Municipal Council Chamber. | N\A | N/A | OPEX | Minutes and Attendance register | Community services
GGPP 22 | Local Aids council meetings | meetings | Implementation HIV/AIDS programmes | BLM | Number Local Aids council meetings held by June 2024 | 4 Local Aids council meeting held by June 2023 | 4 Local Aids council meetings held by June 2024 | 1 Local Aids council meeting held | Target Achieved Local Aids council meeting held on 24 June 2024 at Municipal Council Chamber. | N/A | N/A | OPEX | Minutes and Attendance register | Community services
GGPP 23 | Promote advocacy and stakeholder collaboration | establishment of committees | To Provide support on HIV/AIDS programme | BLM | Number HIV/AIDS ward committees established by June 2024 | 22 ward committees established by June 2023 | 22 HIV/AIDS ward committees established by June 2024 | N/A | Target Achieved HIV/AIDS ward/cluster meeting held on 20,21,25,27 and 28 June 2024 at Cooperspark,Burghreght,kibi moshate and Mongalo village. | N/A | N/A | OPEX | HIV/AIDS Ward committee establishment Report | Community services
GGPP 24 | HIV/AIDS Ward/Cluster meetings | meetings | Promote advocacy and stakeholder collaboration | BLM | Number HIV/AIDS ward/cluster meeting coordinated by June 2024 | 2 HIV/AIDS coordinated by June 2023 | 24 HIV/AIDS ward/cluster meeting coordinated by June 2024 | 6 ward/cluster meeting coordinated | Target Achieved Hast awareness campaign conducted on 23-24 April 2024 at Alldays Village. | N/A | N/A | R 100 000 | HIV/AIDS Cluster meeting reports | Community services
GGPP 25 | Prevent spread of communicable diseases | Hold awareness campaigns | To prevent spread of communicable diseases | BLM | Number HAST awareness campaigns and preventions held by June 2024 | 4 HAST awareness campaigns and preventions held by June 2023 | 4 HAST awareness campaigns and preventions held by June 2024 | 1 HAST awareness campaigns and preventions held | Target Achieved Gender programme meeting held on 22 April 2024 at Blouberg Council Chamber. | N/A | N/A | R 50 000 | HAST awareness reports | Community services
GGPP 26 | Gender Programme | Support to gender programs | To provide support to special focus groups | BLM | Number men and women councils meeting coordinated by June 2024 | Two gender programs support to the gender programs by June 2023 | 4 men and 4 women councils meeting coordinated by June 2024 | 1 men and 1 women councils meeting coordinated | Target Achieved. 01 Men and 01 Women councils held and coordinated on the | N/A | N/A | R 40 000 | Report and attendance registers | Community services
GGPP 27 | Special focus groupings and gender mainstreaming | cordination of events | promote the needs and interests of special focus groupings and gender mainstreaming | BLM | Number gender mainstreaming activities con ducted as per calendar events by June 2024 | Two gender programs supported by June 2023 | 4 gender mainstreaming activities con ducted as per calendar events by June 2024 | 1 gender mainstreaming activities conducted as per calendar events | Target Achieved special focus groupings and gender mainstreaming held on 13 June 2024 at Municipal Chamber . | N/A | N/A | R 40 000 | Gender maintreaming Reports | Community services
GGPP 28 | special focus groupings and gender mainstreaming(capacity building) | Conduct capacity building workshops | To provide support to disability and elderly groups | BLM | Number capacity building workshop conducted by June 2024 | 2 capacity building workshop conducted by June 2023 | 2 capacity building workshop conducted by June 2024 | N/A | N/A | N/A | N/A | R 20 000 | Capacity building Report and attendance registers | Community services
GGPP 29 | Elderly and disability programmes | Coordination of events | To provide support to disability and elderly groups | BLM | Number events coordinated by June 2024 | Two programmes supported by June 2023 | 02 events coordinated by June 2024 | N/A | N/A | N/A | N/A | R 120 000 | Elderly and disability programmes report and attendance registers | Community services
GGPP 30 | Elderly and disability programmes(Council meetings) | meetings | To provide support to disability and elderly groups | BLM | Number elderly and disability council meetings coordinated by June 2024 | 4 elderly and 4 disability council meetings coordinated by June 2023 | 4 elderly and 4 disability council meetings coordinated by June 2024 | 1 elderly and 1 disability council meetings coordinated | Target Achieved Elderly and disability council meetings held on 16 and 23 April 2024 at Municipal westwing boardroom. | N/A | N/A | R 60 000 | Minutes and Attendance register | Community services
GGPP 31 | Elderly and disability programmes(Capacity building) | Workshops | To provide support to disability and elderly groups | BLM | Number capacity building workshop conducted by June 2024 | 02 capacity building workshop conducted by June 2023 | 02 capacity building workshop conducted by June 2024 | N/A | N/A | N/A | N/A | R 80 000 | Capacity building reports | Community services
GGPP 32 | Youth and children programme(Youth Council meetings) | meetings | To provide support to Youth and children | BLM | Number Youth Council meetings held by June 2024 | 4 Youth Council meetings held by June 2023 | 4 Youth Council meetings held by June 2024 | 1 Youth Council meetings held | Target Achieved youth council meetings held 07 June 2024 at Municipal Chamber. | N/A | N/A | R 80 000 | Minutes and Attendance register | Community services
GGPP 33 | Youth and children programme(Back to school campaign) | Conduct the back to school campaign | To provide support to Youth and children | BLM | Number schools visited during back to campaign by June 2024 | Number schools visited during back to campaign by June 2023 | 10 schools visited during back to campaign by June 2024 | N/A | N/A | N/A | N/A | R 50 000.00 | Back to school Report and attendance registers | Community services
GGPP 34 | Youth and children programme(Career guidance and EXPO) | Coordination of event | To provide support to Youth and children | BLM | Number Career guidance and EXPO held by June 2024 | 1 Career guidance and EXPO held by June 2023 | 1 Career guidance and EXPO held by June 2024 | N/A | N/A | N/A | N/A | R 27 000 | Career guidance and EXPO report | Community services
GGPP 35 | Youth and children programme(Commemoration of youth month) | Coordination of event | To provide support to Youth and children | BLM | Number Youth month commemoration event hosted by June 2024 | 1 Youth month commemoration event hosted by June 2023 | 1 Youth month commemoration event hosted by June 2024 | Number Youth month commemoration event hosted by June 2024 | Target Achieved. Youth monht commemoration event hosted on the | N/A | N/A | R70 000 | Youth month commemoration reports | Community services
GGPP 36 | Youth and children programme(Youth capacity building) | Workshops | To provide support to Youth and children | BLM | Number youth capacity building event conducted by June 2024 | 4 youth capacity building event conducted by June 2023 | 4 youth capacity building event conducted by June 2024 | 1 youth capacity building event conducted | Target Achieved youth and children programme capacity building held on 15 June 2024. | N\A | N/A | R 70 000 | Youth capacity building report and attendance registers | Community services
GGPP 37 | Youth and children programme(Children' day) | Support to the children programs | To provide support to Youth and children | BLM | Number children’s day celebrated by June 2024 | Two children’s programs supported by June 2023 | 1 children’s day celebrated by June 2024 | N/A | N/A | N/A | N/A | R 100 000 | Children'day celebration report and attendance registers | Community services
GGPP 38 | Youth and children programme(Take a child to work) | Coordination of event | To provide support to Youth and children | BLM | Number take a child to work campaign conducted by June 2024 | Two children’s programs supported by June 2023 | 01 Take a child to work campaign conducted by June 2024 | Take a child to work campaign conducted by june 2024. | Target Achieved Take a child to work campaign conducted on 15 June 2024 at Ga Tefu village . | N/A | N/A | R 100 000 | take a child to work campaign reports | Community services
GGPP 39 | Mayor – Magoshi | Hosting of Mayor Magoshi | Improved stakeholder relations | BLM | Number Mayor-Magoshi meetings held by June 2024 | 4 Mayor-Magoshi meetings held by June 2023 | 4 Mayor-Magoshi meetings held by June 2024 | 1 Mayor-Magoshi meetings held | Target Achieved Mayor Magoshi held on 06 June 2024. | N\A | N/A | R100 000.00 | Minutes and attendance register | Community services
KPA SPATIAL RATIONALE
NDP | ACTIVE ENGAGEMENT OF CITIZENS IN THEIR OWN DEVELOPMENT
OUTCOME 9 | ACTION SUPPORTIVE TO HUMAN SETTLEMENT(OUTPUT 1)
Project Details
Project/KPI Number | Project Name | Project Description (major activities) | Strategic Objective | Location | Key Performance Indicator | 2022-23 Baseline | 2023-24 Annual Target |  |  |  |  | 2023-24 Budget | Portfolio of evidence | Responsible Department
[8 empty] | Q4 | Actual Perfomance | Reason for Variance | Corrective measure
SPR 09 | Township development | Conduct township establishment process | To formalise rural and urban settlements | BLM | Number of townships developed by June 2024 | 9 townships developed | 1 township developed by June 2024 | Proof of submision of approval of EIA | Target Achieved. Service provider submitted proof of submission for approval of EIA | N/A | N\A | R1.1m | Township development Report | Economic Development and Planning
SPR 10 | Municipal Planning Tribunal | Coordination meetings | To determine land use and and developmentapllications | BLM | Number planning tribunal meetings held by June 2024 | New indicastor | 2 Planning tribunal meetings held by June 2024 | 1 sitting per quarter | Target Achieved, The Municipal Planning Tribunal meeting was held on the 05th June 2024 | N/A | N\A | R150.000 | Municipal tribunal Report | Economic Development and Planning

## SUMMARY OF UNACHIEVED TARG (2
S
SUMMARY OF UNACHIEVED TARGETS
No | TARGET | ACTUAL PERFORMANCE | REASON VARIANCE | CORRECTIVE MEASURE | DEPARTMENT
BSID 1 | 10 Identified sets of Electrical equipment purchased . | Target Not Achieved. 08 Identified sets of Electrical equipment purchased. | Budget constraints | Allocate enough budget for the purchase of the identified set of electrical equipment. | Technical services
BSID 16 | Construction of Access Road and Installation of Power Transformer, NECR and 22KV Switchgear | Target Not Achieved. Construction of Access Road and Installation of Power Transformer, NECR and 22KV Switchgear not done as we still waiting for the delivery of the long lead materials( Transformers and Switchgear Panels) | Manufacturing processes of the materials takes long. | Constant follow-up with the suppliers, to fastrack the delivery of the long lead materials. | Technical services
BSID 17 | Procurement of 05 x 210L emulsion drums, 10 x 20L road marking paints and 500 x 25kg cold mix bags | Target Not Achieved specification and evaluation report done. | Delay in appointment of the service provider | Timeous appoinment of service providers for procurement of materials | Technical services
BSID 29 | Construction of 04 wingwalls | Target Not Achieved. Specification submitted for appoinment of service provider for contruction of wingwalls | Delay in appointment of the service provider | Timeous appoinment of service providers for procurement of materials | Technical services
BSID 40 | 4,4 km construction of Sub-base, base layerworks and interlocking pavement for Mochemi access road and internal street completed bu June 2024 | Target not Achieved.4,4 km construction of Sub-base, base layerworks and interlocking pavement for Mochemi access road and internal street | Delay in delivery of materials from the supplier | constant follow-up with the suppliers, to fastrack the delivery of the materials. | Technical services
BSID 56 | COMPLETION STAGE - Mounting Equipment on the Steel support structures, Stringing of Conductors and Yard Stoning. | Target not Achieved Mounting Equipment on the Steel support structures, Stringing of Conductors and installation of highmast light | Contractor encoutered hard rork on site on | The Contractor was informed to submit the revised catch-up plan in order to ensure that the project is completed by the end of September 2024. | Technical services
BSID 58 | Completion stage:Avon Community centre Completed | Target Not Achieved Qoutation for the remaining scope of work submtted and awaiting aaproval | Contractor terminated | Consultant will be appointed as a turnkey to complete the remaining work | Technical services